WORK ORDER

This Work Order (“Work Order”) is between Sillajen, Inc., a company organized under the laws of Republic of Korea having its principle place of business at floor 9, 109, Sogong-ro, Jung-gu, Seoul, Republic of Korea (“Customer”) and IQVIA RDS East Asia Pte. Ltd., a company organized under the laws of Singapore having its principal place of business at 79 Anson Road, #19-01, Singapore, 079906 (“IQVIA”) and relates to the Master Services Agreement dated July 5, 2024 between Sillajen, Inc. and IQVIA (the “Master Agreement”), which is incorporated by reference herein. Customer and IQVIA are each referred to herein individually as “Party” and collectively as “Parties”.  Pursuant to the Master Agreement, IQVIA has agreed to perform certain Services (as defined below) in accordance with written work orders, such as this one, entered into from time to time.

The Parties hereby agree as follows:

- Work Order.  This document constitutes a “Work Order” under the Master Agreement and this Work Order and the Services contemplated herein are subject to the terms and provisions of the Master Agreement.

- Services and Payment of Fees and Expenses.   The specific Services contemplated by this Work Order (the “Services”) and the related payment terms and obligations are set forth on the following attachments, which are incorporated herein by reference:

SCOPE OF WORK					ATTACHMENT 1

PROJECT BUDGET					ATTACHMENT 2

TIMELINE						ATTACHMENT 3

PAYMENT SCHEDULE				ATTACHMENT 4

TECHNOLOGY TERMS AND CONDITIONS 	ATTACHMENT 5

- IQVIA Technology.  IQVIA Property shall also include its proprietary systems, platforms and applications (collectively, the “IQVIA Technology”). To the extent that IQVIA provides Services using the IQVIA Technology, the technology terms and conditions under Attachment 5 shall apply and certain technology products will involve additional product-specific terms as addressed in this Work Order. Customer grants to IQVIA all rights necessary to use and manage the data entered into the IQVIA Technology. Pursuant to the terms and conditions of this Work Order, Customer  shall have the non-exclusive right, during the term specified herein, to use the IQVIA Technology.  Upon expiration or termination of this Work Order, Customer shall immediately cease use of the IQVIA Technology.  Customer shall have no right to use the IQVIA Technology for any purpose other than specifically allowed under this Work Order. IQVIA makes no representations or warranties as to the accuracy of the data entered into the IQVIA Technology. IQVIA does not warrant that use of the IQVIA Technology will be uninterrupted or error free, nor does IQVIA make any warranty as to the results to be obtained from the use of the IQVIA Technology. EXCEPT AS OTHERWISE SET FORTH IN THE WORK ORDER, THE IQVIA TECHNOLOGY, THE SERVICES AND THE DELIVERABLES DELIVERED HEREUNDER ARE PROVIDED AND DISTRIBUTED ON AN “AS IS” BASIS WITHOUT WARRANTIES OF ANY KIND, EITHER EXPRESS OR IMPLIED, INCLUDING BUT NOT LIMITED TO WARRANTIES OF TITLE, NON-INFRINGEMENT, MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE.

- Term.  The term of this Work Order shall commence on the date of execution and shall continue until the Services described in Attachment 1 are completed, unless this Work Order is terminated in accordance with the Master Agreement.  If the Master Agreement is terminated or expires, but this Work Order is not terminated or completed, then the terms of the Master Agreement shall continue to apply to this Work Order until the Work Order is either terminated or completed.

- Amendments.  No modification, amendment, or waiver of this Work Order shall be effective unless in writing and duly executed and delivered by each Party to the other.

- Currency Exchange. If this Work Order involves the performance of Services by IQVIA or its Affiliates in any country that uses a currency other than the Contract Currency, the Budget for those Services will be based on the local rates in the currency used by IQVIA for pricing in that country (the “Non-Contract Currency”) but converted to and reflected in the Contract Currency. If the portion of the fees based on Non-Contract Currencies exceeds the equivalent of USD $3,000,000 (based on the assumptions in the Budget) in this Work Order, inclusive of executed Change Orders, IQVIA will perform an annual reconciliation (at the anniversary of the effective date of this Work Order each year during the term – the “Contract Anniversary”) of the fees billed in the 12 months prior to the Contract Anniversary compared to the fees that would have been billed based on the application of the Oanda quarterly average Contract Currency exchange rates to Non-Contract Currency fees. The reconciliation will be performed on the final invoice if the term of this Work Order is less than 12 months. If the reconciliation establishes a difference of more than 3%, plus or minus, the amount exceeding 3% will be charged or credited to Customer. By way of example only, if the amount of fees billed in Non-Contract Currencies is $1,000,000 in the 12 months prior to the annual reconciliation, and the annual reconciliation determines that the amount that would have been billed during this same time period utilizing the actual foreign currency exchange rates equals $950,000, then the difference equals $50,000, or 5%. Under this example, IQVIA would credit to Customer the amount of $20,000 ($50,000 – (3% x $1,000,000)).

ACKNOWLEDGED, ACCEPTED AND AGREED TO:

| IQVIA RDS East Asia Pte. Ltd. | Sillajen, Inc. |
| --- | --- |
| By: (signature) | By: (signature) |
| Print Name: | Print Name: |
| Title: | Title: |
| Date: | Date: |

ATTACHMENT 1

SCOPE OF WORK

| IQVIA - SCOPE OF WORK |  |
| --- | --- |
| Client | SillaJen |
| Study Protocol Number | TTK-CS-101 |
| IQVIA Study Reference Number | LAB97701 |
| Investigational Product Name / Number | BAL0891 |
| Study Phase | I |
| Indication | Solid Tumor Configuration |

| STUDY ASSUMPTIONS - SUMMARIZED | WO |
| --- | --- |
| Overall Project Timeline | 61.15 months |
| Countries | KOR, USA |
| Sites Identified | 63 |
| Sites Selected | 13 |
| Sites Activated | 19 |
| Patients Screened | 210 |
| Patients Enrolled | 168 |
| Patients Complete | 152 |
| Screen Fail Rate | 20% |
| Drop Out Rate | 10% |

| Countries | Sites to be Identified by IQVIA | Sites to be Selected by IQVIA | Active Sites | Patients Screened | Patients Enrolled | Patients Completed |
| --- | --- | --- | --- | --- | --- | --- |
| South Korea | 35 | 7 | 11 | 130 | 104 | 94 |
| USA | 28 | 6 | 8 | 80 | 64 | 58 |
| Total Number of Countries: 2 | 63 | 13 | 19 | 210 | 168 | 152 |

| Project Management Study Team - Head Count/FTE | Work Order |
| --- | --- |
| Project Lead (PL) | South Korea PL, 0.47 FTE |
| Project Lead Oversight (PL Oversight) | South Korea PL, 0.08 FTE |
| Transition Lead ( Start-up Only) | South Korea PL, 0.02 FTE |
| Project Management Associate (PMA) | India PMA, 0.35 FTE |
| Clinical Lead (CL) | South Korea CL, 0.48 FTE |
| Clinical Lead (CL) | Brazil CL, 0.35 FTE |
| Clinical Monitoring Lead (CML) | India CML, 0.23 FTE |

| Meetings Overview - Number/Duration of Meetings | Work Order |
| --- | --- |
| Kick-Off (KO) Meeting (Virtual) | 1 Meeting, 8 hours |
| Transition Meetings with Outgoing CRO by CRA | South Korea - 5 Meetings, 1 hour; 2 hours follow up USA - 3 Meetings, 1 hour; 2 hours follow up |
| Internal Site Transition Meetings | South Korea - 5 Meetings, 3 hours USA - 3 Meetings, 3 hours |
| Transition Wrap Up Meetings with Outgoing CRO | South Korea - 5 Meetings, 1 hour; 2 hours follow up USA - 3 Meetings, 1 hour; 2 hours follow up |
| DLRM Meetings | 1 DLRM Kick Off Meeting, 1 hour 1 First DLRM Meeting, 1 hour 15 Subsequent DLRM Meetings, 1 hour |
| Client Teleconferences | 142 Meetings, 1 hour |
| CRA Training | 2 Meetings, 10 hours |
| Note: For meetings which require Face-to-Face attendance, attendee's Travel Time (Labor) will vary based on the region in which the meeting is located, and each attendee's region of origin. |  |
| Scope of Work | Work Order |
| Translations Services |  |
| Documents to be Translated | Protocol, Ethics Committee Letter, Informed Consent Form, Investigator Brochure, Other Patient Documents, Amendments |
| Word Counts | Estimated Total Word Count: 207,100 |
| Word Counts Languages | Korean , Spanish (Latin America) |
| Clinical Monitoring Services - Number & Duration of Visits |  |
| Site Selection Visits - Total | 13 |
| Site Selection Teleconference | 7 (1 hour on call, 2 hours reporting) |
| Site Selection Visits | 6 (4 hours on-site, 5 hours travel, 4 hours reporting) |
| Site Initiation Visits - Total | 11 |
| Site Initiation Visits | 11 (4 hours on-site, 5 hours travel, 6 hours reporting) |
| Interim Monitoring Visits - Total | 553 |
| One Day Onsite Monitoring Visits | 365 (8 hours on-site, 5 hours travel, 6 hours reporting) |
| Two Day Onsite Monitoring Visits | 81 (16 hours on-site, 5 hours travel, 6 hours reporting) |
| One Day Remote SDM Visit | 92 (8 hours on call, 6 hours reporting) |
| Two Day Remote SDM Visit | 15 (16 hours on call, 6 hours reporting) |
| Close Out Visits - Total | 19 |
| Onsite Close-Out Visits | 19 (7 hours on-site, 5 hours travel, 6 hours reporting) |
| Total Site Monitoring Visits | 596 |
| CRF Estimate Detail |  |
| Number of CRFs per drop-out patient | 101 CRF Pages |
| Number of CRFs per complete patient | 169 CRF Pages |
| Total number of CRFs | 27,310 CRF Pages |
| Total number of CRFs to be Source Data Monitored (SDM'd) | 27,310 CRF Pages |
| SDM rate | 100% |
| Investigator Grants |  |
| GrantPlan Range | Medium |

| Activities | Customer or N/A | IQVIA | Scope of Work Description |
| --- | --- | --- | --- |
| GLOBAL SITE ACTIVATION |  |  |  |
| Clinical Trial Regulatory Management: Preparation of Core Submission Package (Project) | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Clinical Trial Regulatory Management: Preparation of Core Submission Package (Country) | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Clinical Trial Regulatory Management: Preparation of Core Submission Package (ICF Project Level) |  | X | IQVIA ICF lead will perform the review and QC of the 3 additional Master ICFs. |
| Clinical Trial Regulatory Management: Preparation of Core Submission Package (Master ICF) |  | X | IQVIA ICF lead will coordinate Main Master ICF Country level adaptations. |
| Clinical Trial Regulatory Management: Preparation of substantial amendment (Project) |  | X | IQVIA Clinical Trial Regulatory Management will consult for and prepare 2 Substantial Amendment(s). |
| Clinical Trial Regulatory Management: Preparation of substantial amendment (ICF Level) |  | X | IQVIA ICF lead to provide support with review of 2 substantial amendment of 4 types ICF (8 master ICF). |
| Clinical Trial Regulatory Management: Preparation of substantial amendment (ICF Country Level) |  | X | IQVIA ICF lead will coordinate with country level adaptation and finalization of Master ICF amendments. |
| Clinical Trial Regulatory Management: Preparation of End of Trial or Clinical Study Report submission / notification (Project) |  | X | Preparation and QC of core submission packages for End of Trial Notification and CSR submission included in the IQVIA's budget. Any additional costs associated with early termination of the trial have not been included in the budget. |
| Global Investigator Contract Service - First Country Amendment |  | X | IQVIA Contract and Budget Solutions Lead will provide support with investigator contract amendment(s) for initial (first) country. |
| Global Investigator Contract Service - Additional Country Amendment |  | X | IQVIA Contract and Budget Solutions Lead will provide support with investigator contract amendment(s) for additional (remaining) countries. |
| Contract and Budget Solutions Lead: Develop Contracting Strategy & Contracting Start-Up Activities |  | X | IQVIA Contract and Budget Solutions Lead will support development of Contracting Strategy & Contracting Start-Up Activities. |
| Contract and Budget Solutions Lead: Budget Approval, Set Payment Terms, Country Guidance Docs |  | X | IQVIA will negotiate and sign on behalf of the customer investigative site clinical trial agreements with site(s) based on pre-approved guidelines provided by the customer. IQVIA may use IQVIA's local CTAs, where local templates have been developed, and IQVIA's global CTA," where such local CTAs are not in place. If IQVIA’s templates are used, the customer may, if required, substitute its own confidentiality, intellectual property, publication provisions, etc. |
| Contract and Budget Solutions Lead: Query Resolution (Contract & Budget) |  | X | IQVIA Contract and Budget Solutions Lead will support site level query resolution (Contracts & Budget). |
| Local RSU (Per Country) - Initial Project setup, RA Submission, Import/Export License |  | X | Country Site Activation – Country level activities for this line in the grid will mostly be related to amending Import/Export Licences, and some administrative tasks, as we expect for other start up activities (RA submissions and ICF adaptations) to be completed by the time this study is transitioned to IQVIA. |
| Local RSU (Initial Sites) - Essential document pack, EC Submission, Site Contracts |  | X | Country Site Activation – Site level (First site) activities for this line in the grid will mostly be related to amending consolidating regulatory and EC documents, and some administrative tasks, as we expect for other start up activities (EC submissions and Initial site contracts) to be completed by the time this study is transitioned to IQVIA. |
| Local RSU (Additional Sites) - Essential document pack, EC Submission, Site Contracts |  | X | Country Site Activation – Site level (Additional sites) activities for this line in the grid will mostly be related to amending consolidating regulatory and EC documents, and some administrative tasks, as we expect for other start up activities (EC submissions and Initial site contracts) to be completed by the time this study is transitioned to IQVIA. |
| Local RSU (Per Country) - RA Notifications |  | X | IQVIA will submit annual periodic reports to the applicable regulatory authorities in the countries/sites where IQVIA is responsible for submissions. Information to be included in the Annual Report will be provided by the customer and/or IQVIA's project team members. Total number of assumed RA notifications is 18. Any costs associated with additional standalone study specific notifications or early termination of the trial have not been included in the budget by default. |
| Local RSU (Initial Site) - EC Notifications |  | X | IQVIA will submit annual periodic reports to the applicable EC in the countries/sites where IQVIA is responsible for submissions (first site). Information to be included in the Annual Report will be provided by the customer and/or IQVIA's project team members. Total number of assumed country EC notifications is 36 (budget for the initial site in country). Any costs associated with additional standalone study specific notifications or early termination of the trial have not been included in the budget by default. |
| Local RSU Master ICF Amendment Adaptation(s) |  | X | IQVIA Country Site Activation team to provide support with 2 country level adaptations of master ICF impacted based upon the amendment requirement. |
| Local RSU Additional ICF(s) Amendment Adaptation(s) |  | X | IQVIA Country Site Activation team to provide support with country level adaptations of additional master ICF (s) impacted based upon the amendment requirement. |
| Local RSU (Additional Site) - EC Notifications |  | X | IQVIA will submit annual periodic reports to the applicable EC in the countries/sites where IQVIA is responsible for submissions (budget for the remaining site(s) in country). Information to be included in the Annual Report will be provided by the customer and/or IQVIA's project team members. Any costs associated with additional standalone study specific notifications or early termination of the trial have not been included in the budget by default. |
| Local RSU (Per Country) - RA Amendments |  | X | Upon request, IQVIA will coordinate, prepare, and submit to the country regulatory authorities 3 global amendment(s) that is/are viewed to affect the safety of the trial subjects or are substantial and likely to alter the interpretation of documentation previously submitted to the authorities. Additional country specific RA amendments may be needed as per the study specific requirements. |
| Local RSU (Initial Site) - EC Amendments |  | X | Upon request, IQVIA will coordinate, prepare, and submit to the country ethic committee 2 trial level amendment(s) that are viewed to affect the safety of the trial subjects or are substantial and likely to alter the interpretation of documentation previously submitted to the authorities (budget for the first site per country). Additional country/site specific EC amendments may be needed as per the study specific requirements. |
| Local RSU (Additional Site) - EC Amendments |  | X | Upon request, IQVIA will coordinate, prepare, and submit to the country/site ECs 2 trial level amendment(s) that is/are viewed to affect the safety of the trial subjects or are substantial and likely to alter the interpretation of documentation previously submitted to the authorities (budget for the remaining sites per country). Additional country/site specific EC amendments may be needed as per the study specific requirements. |
| Local RSU (Initial Site) - Site Contract Amendments |  | X | Upon request, IQVIA will coordinate, and negotiate 1 global contract amendment(s) (budget for the first site per country). Additional country/site specific contracts may be needed as per the study specific requirements. |
| Local RSU (Additional Site) - Site Contract Amendments |  | X | Upon request, IQVIA will coordinate, and negotiate 1 global contract amendment(s) (budget for the remaining sites per country). Additional country/site specific contracts may be needed as per the study specific requirements. |
| DrugDev Feasibility Site Management Technology |  | X | IQVIA DrugDev technology fee for feasibility / site management. |
| Site ID Lead: Study Activity |  | X | IQVIA Site ID lead will support study level activities which may include creation of site ID management plan, CDA template discussions / negotiation, SSQ development, vetting instructions, customer/Internal team communication and reporting. |
| Site ID Lead: Weekly Activity |  | X | On weekly basis, IQVIA site lead will share the status progression reviews and analysis. |
| Site Identification (CDA) |  | X | IQVIA will be responsible for distributing, tracking, negotiating, and collecting CDAs for sites contacted. The budget assumes that up to 63 CDAs will be required to achieve 19 active sites. For Late Phase studies, CDAs may be omitted from the process. The budget includes initial and up to three (3) follow-up contacts with each site, as required to monitor return of documents. |
| Site Identification (SSQ) |  | X | IQVIA will be responsible for distributing, tracking, negotiating, and collecting SSQs for sites contacted. The budget assumes that up to 42 SSQs will be required to achieve 19 active sites. The budget includes initial and up to three (3) follow-up contacts with each site, as required to monitor return of documents. |
| Site List Development |  | X | Site List Development is defined as providing one (1) initial global investigator list that is then used for local country vetting. Site List Development can begin only after all data sources are received. Site List Development includes: Preparing for and participating in strategy development meetings; scoping the project; establishing data pull details and parameters; manage the receipt of data to be included in site list; working with data sources in IQVIA’s site list development tool; QC-ing and tailoring the site list per contracted scope; supporting communications with customer; and, generally, supporting site strategy development in email communications and in meetings. |
| Site Activation Manager Activities |  | X | Global or Primary Site Activation Manager (pSAM/gSAM) activities are related to driving the site activation process and overseeing all tasks from Site ID until Site ready to enroll stage. This role work closely with the other functional leads to coordinate and oversee all requirements for site activation, depending on the study requirements it may include oversight of IRB/EC/RA approval process, site contracts, SIV scheduling, vendor requirements, site training. Including coordination of activities between each of the participating regions/countries to support a consistent approach across the study from site ID to site ready to enroll state. G/P SAM serves as the main point of contact for site activation activities. |
| Regional Site Activation Manager Activities_Site Activity |  | X | Regional Site Activation Manager (rSAM) activities, are related to the submissions and all other site activation tasks from a regional perspective, including budget and contract execution. The SAM serves as the single point of contact for their assigned region/study to co-ordinate communication between site activation and the clinical team. Their daily tasks include planning, staffing, team training, tracking, and reporting the successful execution of the start-up, regulatory, and contract-related activities. From the budgeting perspective tasks are divided into site, country and regional (study) activities. |
| Regional Site Activation Manager Activities_Country Activities |  | X | Regional Site Activation Manager (rSAM) activities, are related to the submissions and all other site activation tasks from a regional perspective, including budget and contract execution. The SAM serves as the single point of contact for their assigned region/study to co-ordinate communication between site activation and the clinical team. Their daily tasks include planning, staffing, team training, tracking, and reporting the successful execution of the start-up, regulatory, and contract-related activities. From the budgeting perspective tasks are divided into site, country and regional (study) activities. |
| Regional Site Activation Manager Activities_Study Activity |  | X | Regional Site Activation Manager (rSAM) activities, are related to the submissions and all other site activation tasks from a regional perspective, including budget and contract execution. The SAM serves as the single point of contact for their assigned region/study to co-ordinate communication between site activation and the clinical team. Their daily tasks include planning, staffing, team training, tracking, and reporting the successful execution of the start-up, regulatory, and contract-related activities. From the budgeting perspective tasks are divided into site, country and regional (study) activities. |
| Substantial Amendment - Initial Country |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with the initial country substantial amendment submission. |
| Substantial Amendment - Additional Country |  | X | IQVIA budget includes oversight support from Maintenance lead (ML) to the project team for the additional country(s) substantial amendment submission. |
| Substantial Amendment - Amendment |  | X | IQVIA Maintenance lead (ML) will review that substantial amendment(s) related activities executed per requirement having collaborated with the project teams closely. |
| Substantial Amendment - Meetings |  | X | On weekly basis, IQVIA Maintenance lead (ML) will have the meeting with project team monitoring that creation and finalization of the action plans are executed as defined and required support provided with the development of project instructions (e.g. Site Activation Management Plan) for the substantial amendments. |
| Substantial Amendment - Country Meetings |  | X | IQVIA Maintenance lead (ML) manages Country Site Activation (CSA) resource identification and supports activities completed by CSA teams. ML will have meetings with country based resources for the substantial amendment related activities and processing the tasks as per plan. |
| Substantial Amendment - Initial EC/CEC submissions |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment EC submission for the initial country. |
| Substantial Amendment - Additional EC/CEC submissions |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment EC submission for the additional country(s). |
| Substantial Amendment - Initial RA submissions |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment regulatory authority submission for the initial country. |
| Substantial Amendment - Additional RA submissions |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment regulatory authority submission for the additional country(s). |
| Substantial Amendment - Initial Country CTA |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment CTA core document submission for the initial country. |
| Substantial Amendment - Additional Country CTA |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment CTA core document submission for the additional country(s). |
| Substantial Amendment - Initial Country ICF |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment ICF submission for the initial country. |
| Substantial Amendment - Additional Country ICF |  | X | IQVIA Maintenance lead (ML) will be providing an oversight support to the project team with substantial amendment ICF submission for the additional country(s). |
| Substantial Amendment - Green Light Form Process Oversight |  | X | IQVIA Maintenance lead (ML) will oversee Green Light Form Process - to check that all prerequisites are completed to allow proper implementation of substantial amendments at the sites. |
| Amendment - Green Light Form Process |  | X | IQVIA Country Site Activation team will collect necessary country / site level documents and complete Green Light Form Process - to check that all prerequisites are in place to allow proper implementation of substantial amendments at the sites. |
| Initial RA Amendment Project Start Up |  | X | Start up for RA team before the first RA Amendment submitted. In IQVIA budget tool, RA start up activities are included in the initial RA Submission. However, IQVIA does not have scope for RA initial submission. Hence, only start up task for RA team is added. |
| INVESTIGATOR PAYMENTS |  |  |  |
| Initial Protocol, Site, and Technology Setup |  | X | IQVIA Clinical Trial Payment (CTP) completes the protocol level set up of the study in our payments system, then completes the vendor/site level set up, including the visit and reimbursable budgets for each site. CTP supports sites through use of regional mailboxes in local language to manage site queries, invoice submissions, and portal support. CTP sets up each site in the payments portal and provide agent access as needed, including customer access. Payment reporting is available on demand in the portal. The sites contract defines the frequency of visit payment processing, including month over month inception to date EDC upload which includes a validation and reconciliation of visit payments. CTP also provides accrual or aggregate spend reporting if requested. Project management support of investigator payments is provided through update calls on a bi-weekly/monthly basis. |
| Payment Processing, Site Support, and Access |  | X | IQVIA Clinical Trial Payment (CTP) will process visit payments to sites per contract terms. Americas sites are paid monthly basis, with all other countries in EMEA and APAC region sites paid on a quarterly basis. In the LATAM region, monthly and quarterly payments may occur, depending on contract language and special requests from sites. Additional charges will be applied to EMEA and APAC sites that negotiate patient visit payment terms that are not quarterly. IQVIA CTP will process reimbursable payments to sites as invoices are received throughout the duration of the study, based on contractual terms. |
| Project Management/Customer Support |  | X | Project management support of investigator payments is provided through update calls on a bi-weekly/monthly basis. |
| Protocol/Site Closeout |  | X | IQVIA Clinical Trial Payment (CTP) assumes all payment activity is completed within 90 days post database lock (DBL). Closeout activities post include communication to sites to submit all final invoices, final reconciliation of visit activity including final proforma submission requests, payment of final reimbursable expenses, release of retainage, and any collection of overpayments. IQVIA will provide site/customer final reporting, which is available in the portal, continued portal access for 90 days after full study closure and provide site support for any questions regarding final payments for 90 days duration. Additional fees will apply should payment activities exceed the 90 days post database locked period. |
| Transparency Reporting (Aggregate Spending) |  | X | Includes the provision of regulatory specific expense information required to fulfill Manufacturer’s submission obligations. These services would include Study Name, Payee Name & Full Address, Primary Investigator information Name & Full Address, Professional designation of the recipient (M.D., D.O., P.A. etc.), Primary Investigator License and Licensed State, National Provider Identifier (NPI US), Description of each item distributed, or service provided, Applicable Comments, Payment Method, Protocol/Project, Site Number, Tax ID (US Teaching Hospital), Taxonomy Coding, Payment Date, Payment Amount, Payment Nature/Purpose, Currency, Payment Reference, Therapeutic Area, Drug, Unique Transaction IDs, Country specific data requirements. Transparency files will be delivered on a quarterly basis, in or around the 15th Business Day after Quarter Closure. Additionally, services pertaining to data reporting formatting will include Country Specific Report(s) breakout upon request, Template Updates/Changes, Data Mapping (required mapping provided by Customer, 30-day notice required), Data resubmissions, Customer Unique IDs (responsibility of Customer to provide file), Additional Fields Specific to Transparency/Disclosure laws. |
| STUDY-SPECIFIC TRAINING SERVICES |  |  |  |
| CRA Training |  | X | IQVIA included time for 8 CRAs to attend project start-up (i.e., protocol review and CRA file setup), therapeutic, and project-specific training. |
| CRA Team Teleconferences During Start-Up |  | X | IQVIA has included CRA Team Teleconferences during start-up to have discussion around the study updates, trends, and issues. |
| CRA Team Teleconferences During Conduct |  | X | IQVIA will perform CRA Team Teleconferences during conduct to have discussion around the study updates, trends, and issues. |
| CLINICAL MONITORING SERVICES - SITE SELECTION TO SITE CLOSE-OUT |  |  |  |
| Site Selection Teleconferences |  | X | IQVIA will perform a total of 7 Site Selection Teleconference Visits. |
| Site Selection Visits |  | X | IQVIA will perform a total of 6 Site Selection Visits. |
| Site Initiation Visits |  | X | IQVIA will perform a total of 11 Site Initiation Visits. |
| One Day Onsite Monitoring Visits |  | X | IQVIA will perform a total of 365 One Day Onsite Monitoring Visits. |
| Two Day Onsite Monitoring Visits |  | X | IQVIA will perform a total of 81 Two Day Onsite Monitoring Visits. |
| Site Management - Start Up |  | X | IQVIA has included budget for CRAs for site management for the active sites. This includes regular site management activities addressing outstanding actions and documents and answering site questions. |
| Site Management - Enrollment |  | X | IQVIA has included budget for CRAs for site management for the active sites. This includes regular site management activities addressing outstanding actions and documents and answering site questions In addition, IQVIA will perform remote EDC review per site month basis. |
| Site Management - Treatment |  | X | IQVIA has included budget for CRAs for site management for the active sites. This includes regular site management activities addressing outstanding actions and documents and answering site questions In addition, IQVIA will perform remote EDC review per site month basis. |
| Site Management - Follow-Up |  | X | IQVIA has included budget for CRAs for site management for the active sites. This includes regular site management activities addressing outstanding actions and documents and answering site questions In addition, IQVIA will perform remote EDC review per site month basis. |
| Site Management - Closeout |  | X | IQVIA has included budget for CRAs for site management for the active sites. This includes regular site management activities addressing outstanding actions and documents and answering site questions. |
| Onsite Close Out Visits |  | X | IQVIA will perform 19 Onsite Close Out Visits. |
| # Remote EDC Review |  | # X | # IQVIA will perform Remote EDC Review on 'per eCRF page' basis depending on the average number of CRF pages and on the average frequency between onsite visits. |
| # One Day Remote SDM Visit |  | # X | # IQVIA will perform 92 One Day Remote SDM visits. |
| # Two Day Remote SDM Visit |  | # X | # IQVIA will perform 15 Two Day Remote SDM visits. |
| Onsite Transition Visits (South Korea) |  | X | IQVIA will perform 5 onsite transition visits. |
| Onsite Transition Visits (USA) |  | X | IQVIA will perform 2 onsite transition visits. |
| Remote Onsite Transition Visits (USA) |  | X | IQVIA will perform 1 remote transition visit. |
| Document Review for Transition- South Korea |  | X | IQVIA will review the document during transition. |
| Document Review for Transition- USA |  | X | IQVIA will review documents during transition. |
| PROJECT MANAGEMENT SERVICES |  |  |  |
| Pre-Project_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Start-Up_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Recruitment_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Treatment_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| In-Treatment Follow-Up_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Database Lock_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Close Out_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| Post Close Out_Clinical Team Management |  | X | IQVIA will assign a Project Lead to oversee IQVIA's project team and activities. IQVIA's Project Lead will serve as customer's primary point of contact. Details about the PM team allocations can be found in the assumptions tab. IQVIA's standard CTMS templates and formats will be used for all reports (e.g., project status reports, monitoring visit reports, etc.) provided during this project. IQVIA will return study documentation to customer at the end of the project. Storage of study documents will be maintained for no more than 90 days following project closure. Original (paper) investigator/site contracts will not be returned to customer or maintained for longer than 90 days. Customer will be responsible for archiving and storage of study documents. |
| DLRT Charter amendment |  | X | IQVIA will amend DLRT charter twice during the study. |
| CENTRALIZED MONITORING SERVICES (CMS) |  |  |  |
| Centralized Monitoring Services Study Management During Conduct |  | X | Central monitoring activities related to site administrative support on all trials. |
| STUDY-FILE MAINTENANCE SERVICES |  |  |  |
| Records Management eTMF Analyst Study Set up and Closure |  | X | TMF analyst acting as eTMF owner, set up of the study TMF via country questionnaires, access control and eTMF closure preparation. |
| Records Management eTMF Analyst Maintenance (FPI-DBL) |  | X | TMF analyst monthly activities related to technical support of the TMF (event execution, access management, document control) during first subject-in to database lock period. |
| Records Management eTMF Analyst Maintenance (DBL - Final Deliverable) |  | X | TMF analyst monthly activities related to technical support of the TMF (event execution, access management, document control, pre-closure checks) during database locked to final deliverable. |
| Records Management eTMF- Quality Project Manager Start-up |  | X | TMF Quality Project Manager supports the Project Leader with the operational set up of the TMF - creation of the TMF Quality plan, relevant TMF instructions, key performance indicators and file review schedule. |
| # Records Management eTMF- Quality Project Manager Maintenance/Closure |  | # X | # TMF Quality Project Manager oversight on quality control and file review performed by records management; review of TMF status; key performance indicators oversight; ensuring file review execution as well as report finalization and supports the TMF closure. |
| # Records Management eTMF Document Administration |  | # X | # IQVIA assumes up to 7975 Documents in the TMF. IQVIA Records Management performs regular independent Quality Control for the foremost of documents ensuring compliance as per IQVIA SOPs and ALCOAC principles. IQVIA Records Management performs regular Comprehensive File Reviews of essential TMF document types. |
| # eTMF - Migrations Per Document |  | # X | # TMF Migration team to upload, index, quality check and file review for 4214 TMF documents from previous CRO. |
| # TMF migration |  | # X | # Migration lead oversight on quality control and file review performed by records management; review of TMF status. |
| # MEDICAL MONITORING SERVICES |  |  |  |
| # Patient Profile Review | # X |  | # Medical Advisor Review of profiles is not included in IQVIA's budget. |
| # Medical Review of Central Lab Alerts | # X |  | # Review of central labs is not included in IQVIA's budget. |
| # Medical Review of Central ECG Alerts | # X |  | # Review of central ECGs is not included in IQVIA's budget. |
| # Pre-Randomization Eligibility Review - Charter Development | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Pre-Randomization Eligibility Review via eDC | # X |  | # IQVIA will not be responsible for eligibility checklist development prior to randomization. |
| # Pre-Randomization Eligibility Review via eDC Summary Report | # X |  | # IQVIA will not be responsible for providing an eligibility summary report. |
| # Pre-Randomization Eligibility Review via SMART Checklist | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Pre-Randomization Eligibility Review -Enhanced | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Pre-Randomization Eligibility Customer TCs | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Pre-Randomization Eligibility Review SMART Checklist Development | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # IVRS Notification and Contact Information maintenance for Eligibility Review | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Pre-Randomization Eligibility Review -External Data Integration | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Medical Start-Up | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Unblinded Medical Monitoring | # X |  | # IQVIA will not be responsible for unblinded medical monitoring. |
| # Medical Monitoring Only Customer Teleconferences | # X |  | # Medical Monitoring Team teleconferences with customer. Meeting minutes preparation is not included in the budget. Preparation of slides is not included in the budget. |
| # Medical Review of Data Listings (FPI - LPO Treatment) | # X |  | # Medical Review Of Listings For Congruency is not included in IQVIA's budget. |
| # Medical Report for Customer (FPI-LPO Treatment) | # X |  | # Medical Report of listing review observations is not included in IQVIA's budget. |
| # Medical Listing Review (LPO Treatment - DBL) | # X |  | # Medical Review Of Listings For Congruency is not included in IQVIA's budget. |
| # Medical Report for Customer (LPO Treatment - DBL) | # X |  | # Medical Report of listing review observations is not included IQVIA's budget. |
| # Specification, Validation and Programming of Listing for Medical Review | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Generation of Listings for Medical Review | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # CRA Training | # X |  | # Customer will be responsible for CRA Training. |
| # Medical Project Administration | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Medical Consulting | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # Medical Surveillance Support | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| # After Hours Medical Coverage | # X |  | # 24 hour on-call coverage is not included in IQVIA's budget. |
| # Medical Review of Coding | # X |  | # Coding review is not included in IQVIA's budget. |
| # Medical Review of Aggregate Data | # X |  | # Medical Evaluation For Safety Signal Detection And Trend Analysis is not included in IQVIA's budget. |
| # Medical Review of Protocol Deviations | # X |  | # Protocol Deviation Review is not included in IQVIA's budget. |
| # Medical Monitor SIV Attendance (Teleconference) | # X |  | # IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| STAR Report | X |  | Medical Evaluation For Safety Signal Detection And Trend Analysis is not included in IQVIA's budget. |
| CRA and Site Support_Start-Up through Closeout | X |  | CRA/Site Support During Business Hours (in the site(s) time zone) is not included in IQVIA's budget. |
| Development of Patient Profile Specifications for IQVIA's Medical Data Review | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Programming of Patient Profiles for IQVIA's Medical Data Review | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Generation of Patient Profiles for IQVIA's Medical Data Review | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Visual Analytics Programming and Maintenance | X |  | IQVIA is not responsible or accountable for this task / activity and has not included any associated scope or budget within this grid. |
| Cisys Set up | X |  | IQVIA will not be responsible for protocol specific set up of the Cisys Platform |
| INFORMATION TECHNOLOGY SERVICES |  |  |  |
| Clinical Analytics & Interface Mapping – Site Fee |  | X | The Clinical Analytics & Interface Mapping service costs relate to the integration of our data sets associated with the trial. IQVIA integrates available data sets (eDC, IVR, etc.) so that there is no reentry of information across systems (including CTMS) and provides a single source of the truth to the project teams. The data supports the internal teams in their conduct of the clinical trial and is used for oversight reporting within the Clinical Analytics application. This also includes the interfacing required for automation of payments to investigators. If the site fee is included for 40 or more sites, then ODI services can be included, if needed. While there may be only a subset of services from this list contracted, or possibly more than listed, Data Integration is still required for services to interoperate. |
| Clinical Analytics & Interface Mapping – Base Fee |  | X | The Clinical Analytics & Interface Mapping service costs relate to the integration of our data sets associated with the trial. IQVIA integrates available data sets (eDC, IVR, etc.) so that there is no reentry of information across systems (including CTMS) and provides a single source of the truth to the project teams. The data supports the internal teams in their conduct of the clinical trial and is used for oversight reporting within the Clinical Analytics application. This also includes the interfacing required for automation of payments to investigators. If the site fee is included for 40 or more sites, then ODI services can be included, if needed. While there may be only a subset of services from this list contracted, or possibly more than listed, Data Integration is still required for services to interoperate. |
| DATA MANAGEMENT SERVICES |  |  |  |
| Data Integration Services |  | X | The Data Integration Services Data Strategists are responsible for managing the integration between source systems (EDC, IRT) and the Data Factory. When the data is integrated it can then be used to power downstream processes, including automated Investigator Payments, population of subject/visit data in CRA trip reports, reporting in Infosario Analytics and powering Centralized Monitoring processes (if scoped). |
| Data Integration Services- SSL Maintenance |  | X | IQVIA will provide maintenance for data acquisition and integration services for a duration of 53 months. |
| MEETINGS |  |  |  |
| Kick Off Meeting |  | X | IQVIA will conduct the Kick-off meeting via Skype/TC |
| Teleconference - Start-up Meeting |  | X | Teleconference Meetings during the start-up phase are included in IQVIA's budget. |
| Teleconference - Conduct |  | X | Teleconference Meetings during the conduct phase are included in IQVIA's budget. |
| Teleconference - Closeout |  | X | Teleconference Meetings during the closeout phase are included in IQVIA's budget. |
| DLRM KOM |  | X | IQVIA will have 1 KOM of DLRM for AML study |
| First DLRM |  | X | IQVIA will support the 1st DLRM. Material preparation, follow up and meeting attendance by PL and CL is included |
| Subsequent DLRM |  | X | IQVIA will support 15 subsequent DLRM. |
| Site Transition Meeting (South Korea) |  | X | IQVIA will provide the 5 site level transition internal meeting between CRA and CTA. |
| Site Transition Meeting (USA) |  | X | IQVIA will provide the 3 site level transition internal meeting between CRA and CTA. |
| Transition Meeting with Outgoing CRO- South Korea |  | X | IQVIA will have 5 site level transition meeting with outgoing CRO by CRA and CL. |
| Transition Meeting with Outgoing CRO- USA |  | X | IQVIA will have 3 site level transition meeting with outgoing CRO by CRA and CL. |
| Transitioning Wrap Up Meeting- South Korea |  | X | IQVIA will have 5 site level transition wrap up meeting with outgoing CRO by CRA and CL. |
| Transitioning Wrap Up Meeting- USA |  | X | IQVIA will have 3 site level transition wrap up meeting with outgoing CRO by CRA and CL. |

ATTACHMENT 2

PROJECT BUDGET

| Project Costs | Budgeting Unit | Number of Units | Cost per Unit USD ($) | Total Cost USD ($) |
| --- | --- | --- | --- | --- |
| Direct Expenses (Core Services) |  |  |  |  |
| Project Start-up/Initiation |  |  |  |  |
| Study Setup and Plan Development | Study | 1 | $10,208.82 | $10,208.82 |
| Project Training | Training | 1 | $122,413.94 | $122,413.94 |
| IQVIA Translation Services | Country | 2 | $30,599.00 | $61,198.00 |
| Sub-total: |  |  |  | $193,820.76 |
| Site Start-up Services |  |  |  |  |
| Site Identified | Site | 11 | $6,058.86 | $66,647.42 |
| Core Document Package - Informed Consent | ICF(s) | 4 | $2,237.57 | $8,950.27 |
| Core Document Package | Core Document Package | 19 | $754.01 | $14,326.11 |
| Core Document Package (for Amendments) Creation and Submission with ICF change | Master ICF Amendment | 8 | $4,106.83 | $32,854.63 |
| Core Document Package (for Notifications) Creation and Submission | Notification | 132 | $189.79 | $25,052.57 |
| Site Activation | Site | 19 | $7,084.02 | $134,596.44 |
| Site Contract | Site | 19 | $2,923.93 | $55,554.68 |
| Site Contract Amendments | Total Contract Amendment | 27 | $1,652.25 | $44,610.84 |
| Clinical Trial Submission to Central and Local IRBs and Ethics Committee(s) | Site | 11 | $3,406.89 | $37,475.78 |
| Substantial Amendment | Amendment | 2 | $65,192.26 | $130,384.51 |
| Import/Export License | License | 1 | $6,521.89 | $6,521.89 |
| RA Amendments | Amendment | 10 | $2,647.58 | $26,475.83 |
| Initial RA Amendment Project Start Up | Study | 1 | $3,689.67 | $3,689.67 |
| Ethics Committee Amendment | Amendment | 54 | $2,206.47 | $119,149.40 |
| ICF Site Info Personalization | Sites | 19 | $224.75 | $4,270.26 |
| Preparation and QC of CSR Submissions | Study | 1 | $806.70 | $806.70 |
| Sub-total: |  |  |  | $711,367.00 |
| Clinical Site Monitoring and Site Management |  |  |  |  |
| Onsite Transition Visits (South Korea) | Transition Visit | 5 | $2,336.79 | $11,683.96 |
| Onsite Transition Visits (USA) | Transition Visit | 2 | $4,050.16 | $8,100.32 |
| Remote Onsite Transition Visits (USA) | Transition Visit | 1 | $2,984.33 | $2,984.33 |
| Document Review for South Korea Transition | Site | 5 | $353.95 | $1,769.75 |
| Document Review for USA Transition | Site | 3 | $632.18 | $1,896.55 |
| Site Qualification Visit | Qual Visit | 6 | $2,325.61 | $13,953.67 |
| Site Qualification Visit by Phone | Qual Call | 7 | $438.11 | $3,066.77 |
| Site Initiation Visit | SIV Visit | 11 | $2,619.94 | $28,819.38 |
| Interim Site Monitoring Visit - One-Day Visits | IMV Visit | 365 | $3,052.53 | $1,114,172.51 |
| Interim Site Monitoring Visit - Two-Day Visits | IMV Visit | 81 | $4,092.57 | $331,497.83 |
| Remote Interim Site Monitoring Visit- One-Day Visit | Remote IMV Visit | 92 | $3,215.90 | $295,862.80 |
| Remote Interim Site Monitoring Visit- Two-Day Visit | Remote IMV Visit | 15 | $5,030.91 | $75,463.65 |
| Essential Document / TMF Maintenance | Enrollment to Follow-up Month | 51 | $9,468.77 | $482,907.32 |
| Site Closeout Visit | Closeout Visits | 19 | $3,742.13 | $71,100.40 |
| Site Management | Site Month | 898 | $676.95 | $607,896.88 |
| Electronic Investigator Site File Software (eISF) | Site | 19 | $2,712.45 | $51,536.53 |
| CTMS Transfer | Study | 1 | $150,000.00 | $150,000.00 |
| Data Integration Services | Study | 1 | $18,326.38 | $18,326.38 |
| Sub-total: |  |  |  | $3,271,039.02 |
| Project Management and Support |  |  |  |  |
| Project Management (Pre-Study) | Pre-study Month | 5 | $73,424.31 | $367,121.56 |
| Project Management (Ongoing) | Enrollment, Treatment Month | 27 | $53,560.49 | $1,446,133.21 |
| Project Management (Closeout) | Closeout Month | 5 | $15,953.26 | $79,766.31 |
| Project Management (Long Term Follow-up ) | Long Term Follow-up/ DBL Month | 25 | $50,463.88 | $1,261,597.02 |
| DLRT Charter Creation and Review | Charter | 2 | $743.66 | $1,487.32 |
| IQVIA DrugDev | Study | 1 | $188,748.20 | $188,748.20 |
| Vendor Management Office | Study | 1 | $213,486.00 | $213,486.00 |
| Sub-total: |  |  |  | $3,558,339.60 |
| Meetings |  |  |  |  |
| Meetings - Kick-off Meeting | Meeting | 1 | $13,595.13 | $13,595.13 |
| Customer Teleconferences | Meeting | 142 | $758.87 | $107,758.93 |
| Meetings - Internal Team Meetings | Meeting* CRA bodies | 1054 | $100.73 | $106,172.93 |
| DLRM | Meeting | 17 | $1,580.93 | $26,875.73 |
| South Korea Transition Meeting with Outgoing CRO | Meeting | 5 | $564.89 | $2,824.46 |
| USA Transition Meeting with Outgoing CRO- USA | Meeting | 3 | $873.79 | $2,621.37 |
| South Korea Site Transition Meeting | Meeting | 5 | $581.34 | $2,906.69 |
| USA Site Transition Meeting | Meeting | 3 | $1,018.81 | $3,056.43 |
| South Korea Transitioning Wrap Up Meeting- South Korea | Meeting | 5 | $750.09 | $3,750.45 |
| USA Transitioning Wrap Up Meeting- USA | Meeting | 3 | $1,217.96 | $3,653.87 |
| LRSU to CRA handover meeting | Site | 11 | $144.12 | $1,585.28 |
| Sub-total: |  |  |  | $274,801.27 |
| End of Study Activities |  |  |  |  |
| Submission of End of Trial Notifications | Site | 19 | $161.25 | $3,063.78 |
| Sub-total: |  |  |  | $3,063.78 |
| Sub-total Direct Costs (Core CRO Services) |  |  |  | $8,012,431.43 |
| Discount (Bottomline) |  |  |  | ($741,196.04) |
| One Time Discount for Work Order only |  |  |  | ($653,067.82) |
| Sub-total Discounted Direct Costs (Core CRO Services) |  |  |  | $6,618,167.57 |
| Pass Through Costs |  |  |  |  |
| Pass Through Costs (Core Services) |  |  |  |  |
| Office Supplies | Notebook | 19 | $ 1,689.21 | $ 32,095.00 |
| Monitoring Travel | Visit | 465 | $ 585.00 | $ 272,025.00 |
| Regulatory/IRB/EC fees | Estimated Total | 19 | $ 14,516.42 | $ 275,811.92 |
| Document Indexing, QC and File Review | Document | 7975 | $ 0.08 | $ 598.13 |
| Printing | Site | 19 | $ 11.26 | $ 214.00 |
| Teleconferences | Teleconference | 264 | $ 21.00 | $ 5,544.00 |
| Miscellaneous Administrative Overhead | active sites x months | 898 | $ 33.00 | $ 29,634.00 |
| Informed Consent Form | ICF | 40 | $ 1,523.25 | $ 60,930.00 |
| DocuSign | Study | 1 | $ 35.36 | $ 35.36 |
| Clario | Study | 1 | $ 416,337.00 | $ 416,337.00 |
| Other Pass-Through Fees |  |  |  |  |
| Investigator Grants and Vendor |  |  |  |  |
| Investigator Payments (North America) | Patient | 80 | $ 43,173.90 | $ 3,453,912.00 |
| Investigator Payments (Asia Pacific) | Patient | 130 | $ 37,442.35 | $ 4,867,505.00 |
| Sub-total Pass-through Costs |  |  |  | $9,414,641.41 |
| Project Grand Total |  |  |  | $16,032,808.97 |

ATTACHMENT 3

TIMELINE

| Project Timelines | Study Phase | Duration | Start Date | End Date |
| --- | --- | --- | --- | --- |
| Pre-Study Activities : ATP/Contract Signed to Final Protocol | Start Up | 0.46 months | 30-Jun-2024 | 14-Jul-2024 |
| Start-Up: Final Protocol to FPI |  | 4.76 months | 15-Jul-2024 | 5-Dec-2024 |
| Recruitment: FPI to LPI | Conduct | 22.56 months | 6-Dec-2024 | 21-Oct-2026 |
| Run-in/Screening: LPI |  | 0.46 months | 22-Oct-2026 | 4-Nov-2026 |
| Treatment: LPI to LPO |  | 4.20 months | 5-Nov-2026 | 11-Mar-2027 |
| Follow-Up: LPIF to LPOF |  | 24.08 months | 12-Mar-2027 | 10-Mar-2029 |
| Locked Database: Last Site Closed to Data Lock |  | 1.00 months | 11-Mar-2029 | 9-Apr-2029 |
| Close-Out: LPO to Last Site Closed | Close | 1.00 months | 10-Apr-2029 | 9-May-2029 |
| Biostatistical Analysis: Database Lock to Final Tables |  | 1.00 months | 10-Apr-2029 | 9-May-2029 |
| Draft Report: Final Tables to 1st Draft Report |  | 1.00 months | 10-May-2029 | 8-Jun-2029 |
| Final Report: Draft Report to Final Report |  | 1.46 months | 9-Jun-2029 | 22-Jul-2029 |
| Post-Study Activities: (Archiving, Document Return) |  | 0.23 months | 23-Jul-2029 | 29-Jul-2029 |
| Total Study Duration, Start and End Date: |  | 61.15 months | 30-Jun-2024 | 29-Jul-2029 |

Note: This timeline is assumption for Work Order budget and actual timeline may change as per project status during the study. Revised timeline will be reflected through a Change Order.

ATTACHMENT 4

PAYMENT SCHEDULE

Professional Fees and Specialty Fees:

Customer agrees to pay IQVIA a maximum amount of USD 6,618,167.57 (Six Million Six Hundred Eighteen Thousand One Hundred Sixty-Seven US Dollars and Fifty-Seven Cents) for Professional and Specialty fees, in conjunction with the services listed in Attachment 1, as per the schedule below:

| Estimated Date | Milestones | Percentage | Net Amount (USD) | Invoice Status |
| --- | --- | --- | --- | --- |
| Jun-2024 | Pre-Payment Due Upon ATP Execution | 4.09% | 270,676.37 | X |
| Aug-2024 | Pre-Payment Due Upon WO Execution | 10.91% | 722,048.76 |  |
| Oct-2024 | Sign off transition checklist | 10.00% | 661,816.76 |  |
| Dec-2024 | First SIV for additional solid tumor site | 9.00% | 595,635.08 |  |
| Feb-2025 | First IRB submission of AML site | 9.00% | 595,635.08 |  |
| Apr-2025 | First IRB approval of AML site | 7.00% | 463,271.73 |  |
| Jun-2025 | 30% of Monitoring Visits & Reports Completed | 7.00% | 463,271.73 |  |
| Aug-2025 | 90% of Site Initiation Visits & Reports Completed | 7.00% | 463,271.73 |  |
| Oct-2025 | 40% of Monitoring Visits & Reports Completed | 7.00% | 463,271.73 |  |
| Dec-2025 | 45% of Monitoring Visits & Reports Completed | 6.00% | 397,090.05 |  |
| Mar-2026 | 50% of Monitoring Visits & Reports Completed | 6.00% | 397,090.05 |  |
| May-2026 | 60% of Monitoring Visits & Reports Completed | 5.00% | 330,908.38 |  |
| Jul-2026 | 65% of Monitoring Visits & Reports Completed | 5.00% | 330,908.38 |  |
| Oct-2026 | 70% of Monitoring Visits & Reports Completed | 4.00% | 264,726.70 |  |
| Jan-2027 | 80% of Monitoring Visits & Reports Completed | 4.00% | 264,726.70 |  |
| Jun-2027 | 85% of Monitoring Visits & Reports Completed | 3.00% | 198,545.03 |  |
| Nov-2027 | 90% of Monitoring Visits & Reports Completed | 3.00% | 198,545.03 |  |
| Jun-2028 | 95% of Monitoring Visits & Reports Completed | 3.00% | 198,545.03 |  |
| Mar-2029 | Completion of In-treatment follow-up of last patient | 3.00% | 198,545.03 |  |
| May-2029 | 100% Site close out | 2.00% | 132,363.35 |  |
| Aug-2029 | Credit of residual Pre-Payment | -15.00% | -992,725.13 |  |
|  | Total | 100.00% | 6,618,167.57 |  |

Investigator Fees:

Total Investigator Grants payable by Customer to IQVIA under this Work Order is USD  8,321,417.00 (Eight Million Three Hundred Twenty-One Thousand Four Hundred Seventeen US Dollars), excluding taxes which will be invoiced monthly based on actual fees incurred by IQVIA in the preceding month.

Upon execution of the Work order, Customer will pay IQVIA an advance of USD  1,248,213.00 (One Million Two Hundred Forty-Eight Thousand Two Hundred Thirteen US Dollars), excluding taxes, to facilitate prompt and timely payments to Investigators. The advance payment shall be reconciled against the actual Investigator Fees paid at the end of the study.

Pass-Through Expenses:

Total Pass-through expense (excluding Investigator Fees) payable by Customer to IQVIA under the Work Order is USD 1,093,224.41 (One Million Ninety-Three Thousand Two Hundred Twenty-Four US Dollars and Forty-One Cents) which will be invoiced monthly based upon the actual expenses incurred by IQVIA in conjunction with the Services of this Work Order.

Upon execution of the Work order Customer will pay IQVIA an advance of USD 137,619.42 (One Hundred Thirty-Seven Thousand Six Hundred Nineteen US Dollars Forty-Two Cents), towards working capital for the pass-through expenses which will be reconciled at the end of the study. Customer has already paid an advance of USD 26,480.58 under the ATP agreement which will be reconciled at the end of study.

If IQVIA incurs pass-through expenses in a currency other than the contracted currency (i.e., USD), then Customer shall reimburse IQVIA for IQVIA’s actual costs in the contracted currency based on the Oanda foreign currency exchange rate (Oanda.com) for the applicable currencies on the last business day of the month immediately preceding the month in which such pass-through expenses are submitted.

Invoicing Details:

IQVIA shall send all invoices to the attention of Finance person at the following address:

Attention to:

Seulgi Lee

Project Manager

SillaJen, Inc.

Email:

BAL0891Phase1INVOICE@kr.sillajen.com

With the exception of any prepayment or advances and investigator invoices, which are due and payable upon receipt of invoice, all other payments shall be made to IQVIA within 30 (thirty) days of receipt of invoice.

Payment to IQVIA must be remitted as follows:

Beneficiary Name : IQVIA RDS East Asia Pte. Ltd.

Bank : 	Citibank NA

Bank Address : 8 Marina View #16-01 Asia Square Tower 1 Singapore 018960

Account No : 	0-709805-045

Swift No. : CITISGSG

All bank charges will be borne by Customer.

Taxes: Customer shall pay all sales and use taxes, including all applicable goods and services tax, value added tax, local taxes, applicable duties, electronic delivery taxes, excise taxes, levies and import fees (collectively, “Taxes”) that are imposed by legislation in connection with the provision of Services and that are not recoverable by IQVIA. All fees set forth in this Work Order are exclusive of Taxes. Where Taxes are paid by IQVIA, IQVIA will provide an invoice showing the Taxes included. Where any Taxes are paid directly to a tax authority or government by Customer, Customer shall not deduct this amount from any amount due to IQVIA. The requirements of this provision shall not apply to any employment-related taxes, duties, income taxes or withholding and shall only apply to Taxes applicable to the Services.

ATTACHMENT 5

TECHNOLOGY TERMS AND CONDITIONS

# DEFINITIONS

“Application Services" means certain IQVIA tech-enabled solutions, software and platforms as set forth in the Work Order and licensed below.

“Authorized User(s)” means Customer, Customer’s affiliates and their individual employees, independent contractors, or any other users authorized or designated by Customer or its affiliates deployed on an IQVIA system, who will have access to and use IQVIA Technology in accordance with this Agreement and/or a Work Order. An individual or entity shall not be an Authorized User unless they have completed IQVIA’s online registration process and the requirements of Section 10 of this Addendum. IQVIA will provide to Customer the necessary network links or other access protocols to enable Customer’s Authorized Users to access IQVIA Technology and/or Technology Services for the period set forth in the applicable Work Order.

“Customer Data” means all data and materials provided by Customer to IQVIA in connection with the provision of the IQVIA Technology or Technology Services.

“Documentation” means IQVIA’s proprietary technical documents or user guides provided by IQVIA as specified in the Work Order to assist Customer in the use of IQVIA Technology or Technology Services.

"Non-SaaS" means certain on-premise IQVIA tech-enabled solutions, software and platforms, as set forth in the Work Order and licensed below.

“SaaS” means Software as a Service as licensed below, with the specifications defined in the Work Order  or published technical documentation of IQVIA.

“Technology Services” means hosting, consulting, configuration, implementation, research, support, maintenance, training of users, and other services performed through or in relation to IQVIA Technology as specified in the Work Order. Customer understands and acknowledges use of the IQVIA Technology by the Customer may require custom services, including, by way of example, software integrations.

“Volume Limitations” shall mean the number of Authorized Users and/or clinical trials set forth on the applicable Work Order.

1. Introduction. This Technology Terms and Conditions Addendum (“Addendum”) supplements the Master Services Agreement (the “Master Agreement ”) with additional terms that apply to the IQVIA Technology and any related Technology Services that are identified in an applicable Work Order, which will be provided to Customer either: (i)  on a SaaS basis; (ii)  through a Non-SaaS basis, or (iii) through Application Services. The Master Agreement and this Addendum collectively are the “Agreement”.  Capitalized terms used herein but not otherwise defined shall have the meanings set forth elsewhere in the Agreement.  Except as otherwise expressly set forth in the Work Order, Customer acknowledges that IQVIA has no delivery obligation for software and will not ship copies of such software to Customer as part of the IQVIA Technology. In the event of a conflict, the order of precedence shall be as follows:

- Product specific terms and conditions set forth in the Work Order;

- this Addendum; and

- the Master Agreement

2. IQVIA Technology and/or Documentation License Grant. Subject to the terms and conditions of this Agreement, and in consideration for the payment of fees set forth in the applicable Work Order, IQVIA grants to Authorized Users, solely during the term of the applicable Work Order, a non-exclusive, non-transferable, non-sublicensable right to access and use the IQVIA Technology and/or Documentation, solely for Customer’s internal business purposes as scoped in the Work Order and pursuant to this Agreement.  This grant is restricted to use by Authorized Users and does not include the right to use IQVIA Technology and/or Documentation on behalf of any third party, except as permitted within the applicable Work Order.  Customer is responsible for procuring and maintaining the network connections that connect Customer to the IQVIA Technology.  Customer agrees that (a) only Authorized Users are permitted to use IQVIA Technology; (b) it is responsible for Authorized Users’ actions or failures to act in connection with activities contemplated under this Agreement and (c) it is required to take all commercially reasonable steps to protect IQVIA Technology and the Documentation from unauthorized use and/or access. Customer grants IQVIA a non-exclusive, royalty free, license to use the logo(s) set out in the Work Order (each, a “Customer Logo”) solely in connection with the provision of IQVIA Technology. IQVIA reserves the right to modify IQVIA Technology, Documentation, and/or Technology Services at any time and agrees to use commercially reasonable efforts to notify Customer of any such modifications to the extent that such modifications materially affect functionality. For clarity purposes, no source code will be provided to Customer unless explicitly required under the applicable Work Order.

3. No Implied Licenses. Customer acknowledges that there are no licenses granted by implication under the Agreement. IQVIA reserves all rights that are not expressly granted. Customer acknowledges that, as between the Parties, IQVIA or its third party licensors own all intellectual property rights and proprietary interests that are embodied in, or practiced by IQVIA Technology, Technology Services, and the Documentation. Any license granted by IQVIA pursuant to the Agreement is only for intellectual property rights  that are owned by IQVIA or that IQVIA has a right to sublicense.

4. Licensed Volume. Customer acknowledges that access and use of IQVIA Technology may be granted to Customer with Volume Limitations.  In the event that IQVIA Technology is used in excess of the Volume Limitations then Customer shall be obligated to pay IQVIA for the number of additional trials and/or Authorized Users in excess of such Volume Limitations at Customer’s then current excess fee rates. Customer may also add licenses for additional Authorized Users or trials by executing a new Work Order.

5. Authorized Users. Customer is responsible for Authorized Users’ compliance with the provisions of this Addendum and the applicable Work Order. IQVIA is not responsible for any harm caused by individuals who were not authorized to have access to IQVIA Technology or Technology Services, and where unauthorized access was caused by Customer, including but not limited to, where such unauthorized individuals were able to gain access because Customer did not request IQVIA to terminate usernames, passwords or accounts on a timely basis or because Customer did not terminate usernames, passwords or accounts on a timely basis in Customer’s local identity management infrastructure or Customer’s local computers. Customer’s or an Authorized User’s intentional violation of the foregoing, or any use of IQVIA Technology or Technology Services in breach of this Agreement by Customer or Authorized Users that in IQVIA’s reasonable judgment imminently threatens the security, integrity or availability of IQVIA Technology or Technology Services  may result in IQVIA’s immediate suspension of the Technology Services. Customer is responsible for Customer’s network connection or service, and issues relating to availability, performance, privacy or security resulting from the use of the network to transmit data.

6. Access and Use. Customer agrees, to the extent applicable with respect to the Technology Services: (i) that Customer is responsible for maintaining the confidentiality of passwords and account information required for access to them; (ii) to immediately notify IQVIA of any unauthorized use of Customer’s account, including but not limited to, breach of security, or loss or theft of Authorized User names or passwords; (iii) that use of IQVIA Technology or Technology Services  is limited to use by Authorized Users for which applicable fees have been paid; (iv) to abide by all applicable local, state, national and international law and regulations, and not to use the IQVIA Technology or Technology Services for any purpose that is unlawful, not contemplated or prohibited under the Agreement; (v) to use commercially reasonable efforts to prevent unauthorized access to, or use of IQVIA Technology or Technology Services; and (vi) to submit Customer Data only in accordance with the applicable Work Order and applicable laws and government regulations. Customer further agrees not to use or permit use of IQVIA Technology or Technology Services, including by uploading, emailing, posting, publishing or otherwise transmitting any material, for any purpose that may: (a) menace or harass any person or cause damage or injury to any person or property; (b) involve the publication of any material that is false, defamatory, harassing or obscene; (c) violate privacy rights; (d) constitute unsolicited bulk e-mail, “junk mail”, “spam” or chain letters; or (e) constitute an infringement of intellectual property or other proprietary rights.

7. Technology Deliverables. As defined in the applicable Work Order, the Technology Services may contemplate issuance by IQVIA to Customer of one or more deliverables, which may include but are not limited to reports and presentations ("Technology Deliverables”). Subject to Customer having complied in full with its obligations set out in the applicable Work Order, the Technology Deliverables will become the property of Customer, with the exclusion of any IQVIA Technology contained therein, which are deemed to be and shall remain the sole and exclusive property of IQVIA (and/or its licensors, as applicable). If any IQVIA Technology is included in or otherwise necessary for the use of any Deliverable provided by IQVIA to Customer under this Agreement, Customer shall have a limited, nonexclusive, non-sublicensable, non-transferable license to use the IQVIA Technology (but not to separate out the IQVIA Technology and sell independently of the Deliverable) contained in the Technology Deliverables internally and solely for its own direct benefit, and only as necessary within and/or in conjunction with such Technology Services or Technology Deliverables, subject to the restrictions set forth herein and any geographic, site, or other use limitations as may be specified in the Work Order.

8. Restrictions. Customer shall not be entitled to receive a source code or object code version of IQVIA Technology or Technology Services.  Except as otherwise specifically permitted in this Agreement, Customer shall not, nor shall it allow any Authorized User or any other person or entity to directly or indirectly: (a) copy, modify, create derivations of or publish IQVIA Technology or Technology Services; (b) use IQVIA Technology or Technology Services in violation of any laws or regulations, including without limitation those related to export controls; (c) market, rent, lease, sell, license, distribute, sublicense or otherwise commercially exploit IQVIA Technology or Technology Services or any Documentation relating thereto provided by IQVIA; (d) authorize the use of IQVIA Technology or Technology Services by others, use IQVIA Technology or Technology Services for the benefit of any third parties, or share user login information or credentials with any third party; (e) copy, modify, create derivative works of, or make any alteration or addition to IQVIA Technology or Technology Services in whole or in part; (f) disassemble, reverse engineer, decode, or decompile IQVIA Technology or Technology Services (except to the extent applicable law prohibits this restriction) or otherwise attempt to discover any portion of the source code related to IQVIA Technology or Technology Services; (g) remove any proprietary notices from IQVIA Technology or Technology Services or Documentation; or (h) access or use IQVIA Technology or Technology Services for purposes of creating a competing SaaS;  (i) use the IQVIA Technology, Technology Services, or Documentation in any manner inconsistent with the Agreement, applicable Work Order, and any laws or regulations; (j) use IQVIA Technology or Technology Services to store or transmit infringing, libelous, obscene, threatening, or otherwise unlawful or tortious material; (k) assign, sublicense, sell, lease or otherwise transfer or convey, or pledge as security or otherwise encumber its rights under the Agreement; (l) use IQVIA Technology or  Technology Services to store or transmit viruses, worms, time bombs, Trojan horses and other harmful or malicious code, files, scripts, agents or programs;  (m) interfere with or disrupt the integrity or performance of IQVIA Technology or Technology Services; or (n) modify, adapt, translate, publicly display, publish or create derivative works of the Documentation or remove any copyright notices, trademark notices, and confidentiality notices.  Except as otherwise expressly permitted in the Work Order, Customer will not, and will not permit Authorized Users or third parties to access or use the IQVIA Technology or Technology Services to operate the business of a third party, or to act as a service bureau or provider of application services to any third party, or to otherwise rent, lease, or use the IQVIA Technology or Technology Services in a resale capacity.

9. IQVIA Proprietary Rights. Customer acknowledges and agrees that the IQVIA Technology, Technology Services and Documentation shall remain the sole and exclusive property of IQVIA (and/or its licensors, as applicable).  IQVIA does not grant, and Customer does not receive, any other interest in any  IQVIA Technology, Technology Services, Documentation or Technology Deliverables, except for those rights explicitly granted under this Addendum or a Work Order. In the event Customer provides IQVIA with feedback or suggestions in respect of the IQVIA Technology, or Technology Services, Customer agrees that such feedback or suggestions will be shared on a non-confidential, nonproprietary basis and IQVIA may choose to use or not use such feedback or suggestions to modify or enhance future IQVIA services without any further obligation to Customer.  IQVIA is free to use such feedback irrespective of any other obligation or limitation between the parties governing such feedback.  Customer hereby assigns and agrees to assign to IQVIA all right, title, and interest in the feedback, and IQVIA is free to use, without any attribution or compensation to any party, any ideas, know-how, concepts, techniques, or other intellectual property rights contained in the feedback, for any purpose. IQVIA shall retain sole and exclusive ownership of the IQVIA Technology,  Technology Services and Documentation, as currently existing or modified over time using such feedback or suggestions, unless otherwise expressly agreed in writing by IQVIA in advance.

10. Subcontractors, Affiliates, Parents and Subsidiaries. Unless it is expressly authorized in the terms of the Master Agreement and/or the applicable Work Order, Customer will not allow any of its independent contractors, affiliates, parent entities or subsidiaries to access or use IQVIA Technology or Technology Services unless Customer has obtained the prior written consent of IQVIA in the applicable Work Order. In the event of the grant of a right to such access or use, Customer hereby represents and warrants to IQVIA that: (i) Customer will ensure that such independent contractors, affiliates, parent entities and subsidiaries will be subject to the terms and restrictions of this Agreement and Work Order to the same extent as the Customer hereunder; and (ii) Customer will be responsible for any and all such access or use by Customer’s independent contractors, affiliates, parent entities and subsidiaries

11. Ownership and Use of Customer Data. Customer will submit Customer Data only in accordance with the applicable Work Order and applicable laws and government regulations. As between Customer and IQVIA, Customer shall be the owner or licensor of any Customer Data provided to IQVIA (other than any Third Party Data) for purposes of providing the Technology Services or input into the IQVIA Technology by Customer. IQVIA acknowledges and agrees that certain other preexisting Customer intellectual property may be utilized by IQVIA to operate and maintain IQVIA Technology or Technology Services and that such pre-existing Customer intellectual property may interact with the IQVIA Technology. As between the Parties, Customer owns such pre-existing Customer intellectual property. IQVIA shall have no right, title or interest in, to or under such Customer intellectual property other than a royalty-free, non-exclusive limited license to use and access such pre-existing Customer intellectual property solely during the term of the applicable Work Order(s) to perform the Technology Services and operate the IQVIA Technology and create the Technology Deliverables in accordance with one or more Work Orders. Customer shall not have any rights in IQVIA Technology and proprietary Technology Services used to create Technology Deliverables. Customer shall only have access to such Customer Data or Technology Deliverables that reside on the platform during the subscription period unless otherwise agreed to by the Parties.

12. Orderly Cessation.  Unless otherwise set forth in a Work Order, immediately upon termination or expiration of the Work Order, IQVIA will cease providing the Technology Services, except such Technology Services as are necessary to transition to another service provider. Should Customer require special transition services, the costs and labor rate for such transition services shall be communicated to Customer with reasonable prior written notice. Such transition services shall be invoiced to Customer pursuant to the provisions of this section and the terms and conditions of this Addendum and the terms and conditions of the Agreement shall remain in full force and effect with respect to such transition for the duration of any such transition services, including but not limited to IQVIA’s obligations regarding return and destruction.

13. Third Party Data (if applicable). The Parties acknowledge and agree that, for the purposes of providing IQVIA Technology and Technology Services, the Customer or its licensor will make available to IQVIA any third party data specified in the Work Order (the “Third Party Data”) for the duration of the Subscription Term of the Work Order, and the Customer hereby acknowledges and agrees that it will, for the duration of the Subscription Term of the Work Order, have in place valid licenses in respect of such Third Party Data and the uses contemplated for such data as set out in the Work Order. Third Party Data shall be Customer Data for purposes of this Agreement.  So long as IQVIA uses the  Third Party Data in accordance with the terms of the Work Order, IQVIA shall have no responsibility and no liability in respect of the provision of the Third Party Data provided to IQVIA or its use by IQVIA or its use by Customer or its independent contractors, affiliates, parent entities or subsidiaries. In the event that IQVIA becomes aware that there is no valid license in place in respect of any Third Party Data and/or that the provision of the services under the Work Order will result in any breach by IQVIA and/or the Customer in respect of any Third Party Data, IQVIA shall have the right to exclude such data from the services to be provided under the Work Order.

14. Third Party Software. For proprietary third party software supplied by and/or embedded in IQVIA Technology, IQVIA grants to Customer a sublicense necessary for Customer to use the IQVIA Technology. Customer agrees that such embedded third party software shall only be utilized by Customer in conjunction with IQVIA Technology. Certain components of IQVIA Technology may be covered by “open source” licenses, as may be indicated in the IQVIA Technology or its related documentation. To the extent required by the licenses covering open source components, the terms of such licenses will apply in lieu of the terms of this Addendum.  Other proprietary third party software that is not supplied by IQVIA but at the Customer’s option is capable of interoperating with the IQVIA Technology may be subject to separate license agreements directly between Customer and the third party licensor. Should Customer elect to use such third party software, Customer is responsible for complying with the requirements of such third party licensor for the third party software, licenses and related terms to take effect. Except as expressly stated otherwise in this Agreement or an applicable Work Order, (i) IQVIA does not provide such third party software to Customer, and (ii) licenses, warranties, indemnification and support for such third party software, if any, will be given by the relevant third party licensors in their license agreements, not by IQVIA.

15. Term and Termination.  IQVIA may terminate a Work Order to which this Addendum applies immediately where any license or confidentiality restrictions, intellectual property rights, data protection provisions, or payment obligations are breached by the Customer. If the applicable Work Order includes Services other than the Technology Services to which this Addendum is applicable, IQVIA may only terminate the Technology Services in accordance with this section and the other Services will continue unaffected unless simultaneously terminated in accordance with the termination rights set forth in the Master Agreement.

16. Indemnification. The Indemnification terms agreed to in the Master Agreement shall not apply to IQVIA Technology offerings. The following language shall instead apply:

16.1 IQVIA Indemnification. IQVIA agrees to indemnify Customer under Work Orders subject of this Addendum, from and against all direct and reasonable costs, expenses, liabilities, claims, losses and damages finally awarded in a court of law against the Customer, or agreed to in writing by IQVIA in settlement, as a direct result of any action or claim that the Customer’s use of the  IQVIA Technology provided by IQVIA in accordance with the Agreement and Work Order infringes the patent, trademark or copyrights of any third party (an “IQVIA Claim”). This section states Customer's sole and exclusive remedy and IQVIA's entire liability for such third party infringement claims.

16.2  IQVIA shall not be required to indemnify Customer to the extent that an IQVIA Claim would be attributable to: (i) modification of IQVIA Technology by Customer or its personnel; (ii) use of IQVIA Technology in a manner inconsistent with the published specifications and/or the instructions given by IQVIA or contrary to the terms of the Agreement or Work Order; (iii) use of IQVIA Technology in combination with any other product or service not provided by IQVIA; (iv) use of IQVIA Technology in a manner not otherwise contemplated by the Agreement or Work Order; (iv) Customer’s use of the Customer Data or Third Party Data in IQVIA Technology or otherwise, (vi) Customer’s use of IQVIA Technology after notice of an IQVIA Claim from IQVIA; (vii) an incident that is a result of Customer’s or its Authorized User’s: (a) failure to follow commercially reasonable safeguards, procedures or protocols reasonably required by IQVIA to safeguard IQVIA Technology from a Security Incident; (b) misuse of IQVIA Technology; (c) gross negligence or intentional misconduct; or (d) breach of applicable data protection laws.

16.3  If Customer is enjoined from using IQVIA Technology or IQVIA reasonably believes it will be enjoined, IQVIA shall have the right, at its sole option, to obtain for Customer the right to continue use of IQVIA Technology or to replace or modify IQVIA Technology so that it is no longer infringing.  If neither of the foregoing options is reasonably available to IQVIA, then use of IQVIA Technology may be terminated at the option of IQVIA, in which event IQVIA’s sole liability shall be to refund to Customer any prepaid fees for IQVIA Technology that were to be provided after the effective date of termination, continue to secure Customer Data as required in the Agreement, and provide all reasonable assistance in the transfer of Customer Data to an alternative provider.

16.4  Customer Indemnification. Except for any claims in respect of which IQVIA is obligated to indemnify Customer as provided above, Customer agrees to indemnify IQVIA and IQVIA’s affiliates from and against all direct and reasonable costs, expenses, liabilities, claims, losses and damages against IQVIA or any IQVIA affiliates, or agreed to in writing by the Customer in settlement, as a direct result of any third-party action or claim (a “Customer Claim”) to the extent arising out of:  (i) Customer’s or an Authorized User’s use of IQVIA Technology other than in accordance with the Agreement or Work Order; (ii) the posting, display, distribution, or other publication or use of Customer Data, Third Party Data or Customer’s logo, including Claims that any such action infringes intellectual property rights of any third party, or (iii) an incident that is a result of Customer’s: (a) failure to follow commercially reasonable safeguards and procedures or protocols reasonably required by IQVIA to safeguard IQVIA Technology from a Security Incident; (b) misuse of IQVIA Technology;  (c) gross negligence or intentional misconduct; or (d) breach of applicable data protection laws.

16.5 If any third party makes an IQVIA Claim or Customer Claim with respect to which the indemnified Party intends to seek indemnification hereunder (each a “Claim”), the indemnified Party shall give prompt written notice of the Claim to the indemnifying Party, including a brief description of the amount and basis for the claim, if known.  Upon receiving such notice, the indemnifying Party shall be obligated to defend the indemnified Party against the Claim and shall be entitled to assume control of the defense and settlement of the Claim.  The indemnified Party may participate in the defense and settlement of the Claim at its own expense, using its own counsel, but without any right of control.  The indemnifying Party shall keep the indemnified Party apprised as to the status of the Claim.  Neither the indemnifying Party nor the indemnified Party shall be liable for any settlement of a Claim made without its consent.  Notwithstanding the foregoing, the indemnified Party shall retain responsibility for all aspects of the Claim that are not subject to indemnification by the other Party hereunder.

17. Audit. The Audit terms agreed to in the Master Agreement shall not apply to IQVIA Technology offerings. Audits of  IQVIA Technology will be negotiated on a case-by-case basis between the Parties separately through the applicable Work Order.

18. Privacy and Security. IQVIA will follow the privacy and security obligations as stated in the Master Agreement (including the terms of the Data Processing Agreement). If Client has elected to use IQVIA’s Single Sign-On service, as indicated in an applicable Work Order, IQVIA will process personal data as a data controller relating to Client’s end users including personal information for the management of the Single Sign-On service. In case of dispute regarding the applicable Work Order and any attached Data Processing Agreement on data privacy and the roles of data controller and data processor in relation to the services included in this paragraph, the stipulations of this paragraph shall supersede.