## 0. Budget Summary
0. Budget Summary (다음 Sheet 입력 시 자동 생성)
Protocol No: TTK-CS-101 |  |  |  | Updated on:
1. Overall Status
| IQVIA | Syneos | Sharp | Fisher | Marken | SBQ | Aptamer | Invivo | Labconnect | AIMS
| CRO CO | Previous CRO CO 현 DMSTAT/PV: 예산은 CD팀에서 관리 | Packaging, Delivery, Destruction, etc | Packaging, Delivery, Destruction, etc | IP Transpotation | PK, SS1 & SS3 | PK, SS2 & SS4 | Biomarker, SS4 | Lab Kit, SS4 | Consulting
Contracted | 15935420.47 |  | 675051 | 249693702 | 132368849 | 440404.83 | 294600000 | 490894 | 68277 | 367130000
Paid | 3144815.93 | 0 | 472838.16 | 15142569 | 132368849 | 160795.18 | 54450000 | 213142.36 | 45962.23 | 250597600
Remaining | 12790604.54 |  | 202212.84 | 234551133 | 0 | 279609.65 | 240150000 | 277751.64 | 22314.77 | 116532400
% | 80.27% |  | 29.96% | 93.94% | 0% | 63.49% | 81.52% | 56.58% | 32.68% | 31.74%
2. Yearly/Quarterly Plan and Payment Status
Vendor | Currency | 2023 | [10 empty] | 2024 | [10 empty] | 2025 | [10 empty] | 2026 | [10 empty] | 2027
|  | 1Q (Jan~Mar) |  | 2Q (Apr~Jun) |  | 3Q (Jul~Sep) |  | 4Q (Oct~Dec) |  | 2023 |  |  | 1Q (Jan~Mar) |  | 2Q (Apr~Jun) |  | 3Q (Jul~Sep) |  | 4Q (Oct~Dec) |  | 2024 |  |  | 1Q (Jan~Mar) |  | 2Q (Apr~Jun) |  | 3Q (Jul~Sep) |  | 4Q (Oct~Dec) |  | 2025 |  |  | 1Q (Jan~Mar) |  | 2Q (Apr~Jun) |  | 3Q (Jul~Sep) |  | 4Q (Oct~Dec) |  | 2026 |  |  | 1Q (Jan~Mar) |  | 2Q (Apr~Jun) |  | 3Q (Jul~Sep) |  | 4Q (Oct~Dec) |  | 2027
|  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Delta (Δ) | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Delta (Δ) | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Delta (Δ) | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Delta (Δ) | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Delta (Δ)
CRO(IQVIA) | USD | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 297156.95 |  | 2772763.95 | 0 | 3069920.9 | -3069920.9 |  | 34695.35 |  | 656709.24 |  | 829858.16 | 772849 | 2380983.1 | 772849 | 3902245.85 | -3129396.85 | 1050743 | 1305306.74 | 437810 | 1431538.78 | 437810 | 134077.92 | 350243 | 0 | 2276606 | 2870923.44 | -594317.44 | 350243 | 0 | 262686 | 0 |  | 0 |  | 0 | 612929 | 0 | 612929
CRO(Syneos) | USD |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 364505 | 0 | 364505 | 0 | 364505 | 543464 | 0 | 452886 | 0 | 377405 | 0 | 314504 | 0 | 1688259 | 0 | 1688259 | 262087 | 0 |  | 0 | 262087 | 0 |  | 0 | 524174 | 0 | 524174
Sharp | USD |  | 12267 |  | 16333.47 |  | 46052.33 |  | 20282.86 | 0 | 94935.66 | -94935.66 |  | 7522.83 |  | 49874.57 |  | 41664.66 |  | 31336.49 | 0 | 130398.55 | -130398.55 |  | 25424.65 |  | 68361.41 |  | 100122.42 |  | 53595.47 | 0 | 247503.95 | -247503.95 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Fisher | KRW | [8 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 4838959 |  | 10303610 | 0 | 4838959 | -4838959 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
Marken | KRW |  | 0 |  | 6832940 |  | 42000 |  | 0 | 0 | 6874940 | -6874940 |  | 0 |  | 29201942 |  | 0 |  | 10670790 | 0 | 39872732 | -39872732 |  | 0 |  | 2942881 |  | 39794243 |  | 42884053 | 0 | 85621177 | -85621177 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
SBQ | CHF |  | 67333.98 |  | 0 |  | 1968 |  | 0 | 0 | 69301.98 | -69301.98 |  | 0 |  | 0 |  | 0 |  | 4750 | 0 | 4750 | -4750 |  | 6213.6 |  | 70413.6 |  | 0 |  | 0 | 0 | 76627.2 | -76627.2 | 50182 | 0 | 50182 | 10116 | 50182 | 0 | 50182 | 0 | 200728 | 10116 | 190612 | 50182 | 0 | 50182 | 0 | 50182 | 0 | 50182 | 0 | 200728 | 0 | 200728
Aptamer | KRW | [8 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 0 |  | 14190000 |  | 0 | 36600000 | 40260000 | 36600000 | 54450000 | -17850000 | 33777000 | 0 | 59577000 | 0 | 43377000 | 0 | 28377000 | 0 | 165108000 | 0 | 165108000 | 35154000 | 0 | 38700000 | 0 |  | 0 |  | 0 | 73854000 | 0 | 73854000
Invivo | USD | [8 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 166689 | 10499 | 17748.87 | 10499 | 184437.87 | -173938.87 | 15748 | 13484.15 | 15748 | 15220.34 | 15748 | 0 | 15748 | 0 | 62992 | 28704.49 | 34287.51 | 20998 | 0 |  | 0 |  | 0 |  | 0 | 20998 | 0 | 20998
Labconnect | USD | [8 empty] | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 45130 | 5413 | 832.23 | 5413 | 45962.23 | -40549.23 | 8120 | 0 | 8120 | 0 | 8120 | 0 | 8120 | 0 | 32480 | 0 | 32480 | 10826 | 0 |  | 0 |  | 0 |  | 0 | 10826 | 0 | 10826
AIMS | KRW |  | 0 |  | 0 |  | 0 |  | 23650000 | 0 | 23650000 | -23650000 |  | 0 |  | 0 |  | 53399500 |  | 46695000 | 0 | 100094500 | -100094500 |  | 50160000 |  | 23650000 |  | 0 |  | 44067100 | 0 | 117877100 | -117877100 | 33000000 | 8976000 |  | 0 | 9075000 | 0 |  | 0 | 42075000 | 8976000 | 33099000 | 12500000 | 0 | 12500000 | 0 | 12500000 | 0 | 12500000 | 0 | 50000000 | 0 | 50000000
Total (KRW) | KRW | 0 | 0 | 0 | 6832940 | 0 | 42000 | 0 | 23650000 | 0 | 30524940 | -30524940 | 0 | 0 | 0 | 29201942 | 0 | 53399500 | 0 | 57365790 | 0 | 139967232 | -139967232 | 0 | 50160000 | 0 | 40782881 | 0 | 44633202 | 36600000 | 137514763 | 36600000 | 262787236 | -226187236 | 66777000 | 8976000 | 59577000 | 0 | 52452000 | 0 | 28377000 | 0 | 207183000 | 8976000 | 198207000 | 47654000 | 0 | 51200000 | 0 | 12500000 | 0 | 12500000 | 0 | 123854000 | 0 | 123854000
Total (USD) | USD | 0 | 12267 | 0 | 16333.47 | 0 | 46052.33 | 0 | 20282.86 | 0 | 94935.66 | -94935.66 | 0 | 7522.83 | 0 | 49874.57 | 0 | 338821.61 | 0 | 2804100.44 | 0 | 3200319.45 | -3200319.45 | 0 | 60120 | 0 | 725070.65 | 0 | 1141799.58 | 1153266 | 2453159.67 | 1153266 | 4380149.9 | -3226883.9 | 1618075 | 1318790.89 | 914564 | 1446759.12 | 839083 | 134077.92 | 688615 | 0 | 4060337 | 2899627.93 | 1160709.07 | 644154 | 0 | 262686 | 0 | 262087 | 0 | 0 | 0 | 1168927 | 0 | 1168927
Total (CHF) | CHF | 0 | 67333.98 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 69301.98 | -69301.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750 | 0 | 4750 | -4750 | 0 | 6213.6 | 0 | 70413.6 | 0 | 0 | 0 | 0 | 0 | 76627.2 | -76627.2 | 50182 | 0 | 50182 | 10116 | 50182 | 0 | 50182 | 0 | 200728 | 10116 | 190612 | 50182 | 0 | 50182 | 0 | 50182 | 0 | 50182 | 0 | 200728 | 0 | 200728

## 1. IQVIA
1. CRO: IQVIA |  |  |  |  | 1-1, 1-2 입력 시 자동 기입되는 페이지
| Contract Number: | LAB97701 | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | $ | %
Budget | 15935420.47
Paid | 7387992.21 | 46.36%
Remaining | 8547428.26 | 53.64%
2. Total Yearly and Monthly Payment
| USD | KRW
2024 | 3069920.9 | 652255797
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 297156.95 | 0 | 2108320.73 | 0 | 664443.22
0 | 0 | 0 | 0 | 0 | 0 | 0 | 445735425 | 0 | 206474715 | 0 | 45657
2025 | 3902245.85 | 275739
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
2603.63 | 3495.17 | 28596.55 | 602035.01 | 22753.1 | 31921.13 | 280003.73 | 549854.43 | 0 | 0 | 270614.14 | 2110368.96
0 | 0 | 0 | 45768 | 0 | 0 | 0 | 45891 | 0 | 0 | 45999 | 138081
2026 | 2870923.44 | 184578
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
429677.89 | 471496.93 | 404131.92 | 253068.95 | 112404.17 | 1066065.66 | 134077.92 | 0 | 0 | 0 | 0 | 0
0 | 46081 | 46096 | 0 | 0 | 92401 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Contract Details
Team FTE | Initial | Country | CO1 | Country
Project Lead (PL) |  |  | 0.54 | KR
PL Oversight |  |  | 0.08 | KR
Transition Lead |  |  | 0.01 | KR
Project Management Associate (PMA) |  |  | 0.34 | IN
Clinical Lead (CL) KR |  |  | 0.54 | KR
Clinical Lead (CL) US |  |  | 0.39 | BR
Clinical Monitoring Lead (CML) |  |  | 0.27 | IN
| Initial |  |  | CO1 |  |  | Change
Milestones | Duration(Months) | Start Date | End Date | Duration(Months) | Start Date | End Date | Initial to CO1
Pre-Study Activities : ATP/Contract Signed to Final Protocol |  |  |  | 0.46 | 2024-06-30 | 2024-07-14 | -0.46
Start-Up: Final Protocol to FPI |  |  |  | 2.56 | 2024-07-15 | 2024-09-30 | -2.56
Recruitment: FPI to LPI |  |  |  | 24.72 | 2024-10-01 | 2026-10-21 | -24.72
Run-in/Screening: LPI |  |  |  | 0.46 | 2026-10-22 | 2026-11-04 | -0.46
Treatment: LPI to LPO |  |  |  | 4.2 | 2026-11-05 | 2027-03-11 | -4.2
Follow-Up: LPIF to LPOF |  |  |  | 24.08 | 2027-03-12 | 2029-03-10 | -24.08
Locked Database: Last Site Closed to Data Lock |  |  |  | 1 | 2029-03-11 | 2029-04-09 | -1
Close-Out: LPO to Last Site Closed |  |  |  | 1 | 2029-04-10 | 2029-05-09 | -1
Biostatistical Analysis: Database Lock to Final Tables |  |  |  | 1 | 2029-04-10 | 2029-05-09 | -1
Draft Report: Final Tables to 1st Draft Report |  |  |  | 1 | 2029-05-10 | 2029-06-08 | -1
Final Report: Draft Report to Final Report |  |  |  | 1.46 | 2029-06-09 | 2029-07-22 | -1.46
Post-Study Activities: (Archiving, Document Return) |  |  |  | 0.23 | 2029-07-23 | 2029-07-29 | -0.23
Total Study Duration, Start and End |  |  |  | 61.17 | 2024-06-30 | 2029-07-29 | -61.17
Direct Costs by Milestones
Initial | % | Amount | CO1 | % | Amount
|  |  | Pre-Payment Due Upon ATP Execution | 4.02 | 270676.37
|  |  | Pre-Payment Due Upon WO Execution | 10.72 | 722048.76
|  |  | Sign off transition checklist | 9.83 | 661816.76
|  |  | First IRB submission of AML site | 8.84 | 595635.08
|  |  | First IRB approval of AML site | 6.88 | 463271.73
|  |  | Pre-payment upon CO1 Execution | 0.26 | 17605
|  |  | First SIV for additional solid tumor site | 9 | 606207.57
|  |  | 30% of Monitoring Visits & Reports Completed | 7 | 471496.93
|  |  | 80% of Site Initiation Visits & Reports Completed | 7 | 471496.93
|  |  | 25% of Monitoring Visits & Reports Completed | 7 | 471496.93
|  |  | 35% of Monitoring Visits & Reports Completed | 6 | 404131.92
|  |  | 40% of Monitoring Visits & Reports Completed | 6 | 404131.92
|  |  | 50% of Monitoring Visits & Reports Completed | 5 | 336776.59
|  |  | 55% of Monitoring Visits & Reports Completed | 5 | 336776.59
|  |  | 65% of Monitoring Visits & Reports Completed | 4 | 269421.27
|  |  | 75% of Monitoring Visits & Reports Completed | 4 | 269421.27
|  |  | 80% of Monitoring Visits & Reports Completed | 3 | 202065.95
|  |  | 90% of Monitoring Visits & Reports Completed | 3 | 202065.95
|  |  | 95% of Monitoring Visits & Reports Completed | 3 | 202065.95
|  |  | Completion of In-treatment follow-up of last patient | 3 | 202065.95
|  |  | 100% Site close out | 2.45 | 165186.48
|  |  | Credit of residual Pre-Payment | -15 | -1010330.13
Total | 100 |  | Total | 100 | 6735531.77
*이 외, PTC(Core Services + Investigator Grants and Vendor)는 계약서 참고

## 1-1. Direct
1. CRO: IQVIA
| Contract Number: | LAB97701 | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Sub Total Direct Cost Status
Category | $ | %
Budget | 6735531.77
Paid | 5896792.52 | 87.55%
Remaining | 838739.25 | 12.45%
2. Direct Cost Yearly and Monthly Payment
| USD | KRW
2024 | 1654541.89 | 406105797
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 270676.37 | 0 | 722048.76 | 0 | 661816.76
0 | 0 | 0 | 0 | 0 | 0 | 0 | 406014555 | 0 | 45585 | 0 | 45657
2025 | 2625713.27 | 275739
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 595635.08 | 0 | 0 | 0 | 463271.73 | 0 | 0 | 17605 | 1549201.46
0 | 0 | 0 | 45768 | 0 | 0 | 0 | 45891 | 0 | 0 | 45999 | 138081
2026 | 1616537.36 | 184578
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 471496.93 | 404131.92 | 0 | 0 | 740908.51 | 0 | 0 | 0 | 0 | 0 | 0
0 | 46081 | 46096 | 0 | 0 | 92401 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Direct Costs Details
Milestones | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) | Paid (Y) | 지출결의 #
Pre-Payment Due Upon ATP Execution | 270676.37 | 270676.37 | SGP-030213 | 2024-07-22 | 2024 | 8 | 2024-08-08 | 406014555 | Y | CD24-170
Pre-Payment Due Upon WO Execution | 722048.76 | 722048.76 | SGP-030533 | 2024-09-27 | 2024 | 10 | 2024-10-10 | 45585 | Y | CD24-220
Sign off transition checklist | 661816.76 | 661816.76 | SGP-030822 | 2024-11-29 | 2024 | 12 | 2024-12-19 | 45657 | Y | CD24-277
First IRB submission of AML site | 595635.08 | 595635.08 | SGP-031343 | 2025-04-08 | 2025 | 4 | 2025-04-17 | 45768 | Y | CD25-072
First IRB approval of AML site | 463271.73 | 463271.73 | SGP-031701 | 2025-07-14 | 2025 | 8 | 2025-08-14 | 45891 | Y | CD25-155
Pre-payment upon CO1 Execution | 17605 | 17605 | SGP-032017 | 2025-10-08 | 2025 | 11 | 2025-11-27 | 45999 | Y | CD25-205
First SIV for additional solid tumor site | 606207.57 | 606207.57 | SGP-032306 | 2025-12-10 | 2025 | 12 | 2025-12-24 | 46027 | Y | CD25-232
30% of Monitoring Visits & Reports Completed | 471496.93 | 471496.96 | SGP-032306 | 2025-12-10 | 2025 | 12 | 2025-12-24 | 46027 | Y | CD25-232
80% of Site Initiation Visits & Reports Completed | 471496.93 | 471496.93 | SGP-032465 | 2026-01-20 | 2026 | 2 | 2026-02-26 | 46081 | Y | CD26-016
25% of Monitoring Visits & Reports Completed | 471496.93 | 471496.93 | SGP-032175 | 2025-11-09 | 2025 | 12 | 2025-12-24 | 46027 | Y | CD25-225
35% of Monitoring Visits & Reports Completed | 404131.92 | 404131.92 | SGP-032533 | 2026-02-10 | 2026 | 3 | 2026-03-12 | 46096 | Y | CD26-023
40% of Monitoring Visits & Reports Completed | 404131.92 | 404131.92 | SGP-032889 | 2026-05-13 | 2026 | 6 | 2026-06-04 | 46183 | Y | CO26-025
50% of Monitoring Visits & Reports Completed | 336776.59 | 336776.59 | SGP-032978 | 2026-06-10 | 2026 | 6 | 2026-07-09 | 46218 | Y | CO26-045
55% of Monitoring Visits & Reports Completed | 336776.59 | [6 empty] | 0
65% of Monitoring Visits & Reports Completed | 269421.27 | [6 empty] | 0
75% of Monitoring Visits & Reports Completed | 269421.27 | [6 empty] | 0
80% of Monitoring Visits & Reports Completed | 202065.95 | [6 empty] | 0
90% of Monitoring Visits & Reports Completed | 202065.95 | [6 empty] | 0
95% of Monitoring Visits & Reports Completed | 202065.95 | [6 empty] | 0
Completion of In-treatment follow-up of last patient | 202065.95 | [6 empty] | 0
100% Site close out | 165186.48 | [6 empty] | 0
Credit of residual Pre-Payment | -1010330.13 | [6 empty] | 0

## 1-2. PTC
1. CRO: IQVIA
| Contract Number: | LAB97701 | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Sub Total PTC Status
Category | $ | %
Budget | 9199888.7
Advance(Deposit) |  |  | 연구 종료 시 Reconcilation 예정이므로 paid에서 제외
Paid | 1491199.69 | 16.21%
Remaining | 7708689.01 | 83.79%
2. PTC Yearly and Monthly Payment
| USD | KRW
2024 | 1415379.01 | 246150000
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 26480.58 | 0 | 1386271.97 | 0 | 2626.46
0 | 0 | 0 | 0 | 0 | 0 | 0 | 39720870 | 0 | 206429130 | 0 | 0
2025 | 1276532.58 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
2603.63 | 3495.17 | 28596.55 | 6399.93 | 22753.1 | 31921.13 | 280003.73 | 86582.7 | 0 | 0 | 253009.14 | 561167.5
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 1254386.08 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
429677.89 | 0 | 0 | 253068.95 | 112404.17 | 325157.15 | 134077.92 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. PTC details
Budget | 1437069.78 | 26740 | 267560 | 421115.32 | 498.6 | 171 | 5544 | 24717 | - | 39.78 | 556302 | 62192 | 3467289 | 4367720
Invoiced | 3946297.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remaining | -2509227.89 | 26740 | 267560 | 421115.32 | 498.6 | 171 | 5544 | 24717 | #VALUE! | 39.78 | 556302 | 62192 | 3467289 | 4367720
Remaining (%) |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | #VALUE! | 100% | 100% | 100% | 100% | 100%
Invoice # | Deposit (Budget 미포함) | Office Supplies | Monitoring Travel | Regulatory/IRB/EC fees | Document Indexing, QC and File Review | Printing | Teleconferences | Miscellaneous Administrative Overhead | Informed Consent Form | DocuSign | Clario | Investigator Meetings Logistics | Investigator Payments (North America) | Investigator Payments (Asia Pacific) | Invoiced Amount($) | Invoiced Date | Paid Year | Paid Month | Paid Date | Paid Amount(₩) | Paid (Y) | 지출결의 #
SGP-030212 | 26480.58 | [13 empty] | 26480.58 | 2024-07-22 | 2024 | 8 | 2024-08-08 | 39720870 | Y | CD24-170
SGP-030531 | 137619.42 | [13 empty] | 137619.42 | 2024-09-27 | 2024 | 10 | 2024-10-10 | 206429130 | Y | CD24-220
SGP-030532 | 1248213 | [13 empty] | 1248213 | 2024-09-27 | 2024 | 10 | 2024-10-10 |  | Y | CD24-220
SGP-030621 | 439.55 | [13 empty] | 439.55 | 2024-10-15 | 2024 | 10 | 2024-10-24 |  | Y | CD24-225
SGP-030789 | 2626.46 | [13 empty] | 2626.46 | 2024-11-21 | 2024 | 12 | 2024-12-05 |  | Y | CD24-277
SGP-030941 | 2603.63 | [13 empty] | 2603.63 | 2024-12-26 | 2025 | 1 | 2025-01-02 |  | Y | CD24-289
SGP-031090 | 3495.17 | [13 empty] | 3495.17 | 2025-02-11 | 2025 | 2 | 2025-02-20 |  | Y | CD25-034
SGP-031208 | 28596.55 | [13 empty] | 28596.55 | 2025-03-05 | 2025 | 3 | 2025-03-20 |  | Y | CD25-045
SGP-031300 | 6399.93 | [13 empty] | 6399.93 | 2025-03-24 | 2025 | 4 | 2025-04-17 |  | Y | CD25-069
SGP-031418 | 22753.1 | [13 empty] | 22753.1 | 2025-04-28 | 2025 | 5 | 2025-05-22 |  | Y | CD25-086
SGP-031520 | 25045.7 | [13 empty] | 25045.7 | 2025-05-22 | 2025 | 6 | 2025-06-19 |  | Y | CD25-101
SGP-031521 | 6875.43 | [13 empty] | 6875.43 | 2025-05-22 | 2025 | 6 | 2025-06-19 |  | Y | CD25-101
SGP-031653 | 246916.46 | [13 empty] | 246916.46 | 2025-07-04 | 2025 | 7 | 2025-07-31 |  | Y | CD25-137
SGP-031654 | 33087.27 | [13 empty] | 33087.27 | 2025-07-04 | 2025 | 7 | 2025-07-31 |  | Y | CD25-137
SGP-031763 | 27051.47 | [13 empty] | 27051.47 | 2025-07-28 | 2025 | 8 | 2025-08-31 |  | Y | CD25-154
SGP-031764 | 59531.23 | [13 empty] | 59531.23 | 2025-07-28 | 2025 | 8 | 2025-08-31 |  | Y | CD25-154
SGP-032098 | 24756.78 | [13 empty] | 24756.78 | 2025-10-17 | 2025 | 12 | 2025-12-11 |  | Y | CD25-219
SGP-032002 | 38305.79 | [13 empty] | 38305.79 | 2025-09-25 | 2025 | 11 | 2025-11-27 |  | Y | CD25-205
SGP-032003 | 214703.35 | [13 empty] | 214703.35 | 2025-09-25 | 2025 | 11 | 2025-11-27 |  | Y | CD25-205
SGP-032143 | 266838.75 | [13 empty] | 266838.75 | 2025-11-07 | 2025 | 12 | 2025-12-11 |  | Y | CD25-212
SGP-032144 | 32289.36 | [13 empty] | 32289.36 | 2025-11-07 | 2025 | 12 | 2025-12-11 |  | Y | CD25-212
SGP-032257 | 212960.76 | [13 empty] | 212960.76 | 2025-11-27 | 2025 | 12 | 2025-12-11 |  | Y | CD25-219
SGP-032258 | 24321.85 | [13 empty] | 24321.85 | 2025-11-27 | 2025 | 12 | 2025-12-11 |  | Y | CD25-219
SGP-032353 | 418111.57 | [13 empty] | 418111.57 | 2025-12-19 | 2026 | 1 | 2026-01-08 |  | Y | CD26-001
SGP-032354 | 11566.32 | [13 empty] | 11566.32 | 2025-12-19 | 2026 | 1 | 2026-01-08 |  | Y | CD26-001
SGP-032593 | 183170.01 | [13 empty] | 183170.01 | 2026-03-06 | 2026 | 4 | 2026-04-09 |  | Y | CO26-001
SGP-032594 | 69898.94 | [13 empty] | 69898.94 | 2026-03-06 | 2026 | 4 | 2026-04-09 |  | Y | CO26-001
SGP-032690 | 82636.67 | [13 empty] | 82636.67 | 2026-03-24 | 2026 | 5 | 2026-05-07 |  | Y | CO26-006
SGP-032689 | 18197.63 | [13 empty] | 18197.63 | 2026-03-24 | 2026 | 5 | 2026-05-07 |  | Y | CO26-006
SGP-032827 | 11569.87 | [13 empty] | 11569.87 | 2026-04-24 | 2026 | 5 | 2026-05-21 |  | Y | CO26-019
SGP-032940 | 298480.73 | [13 empty] | 298480.73 | 2026-06-09 | 2026 | 6 | 2026-06-18 |  | Y | CO26-034
SGP-032941 | 26676.42 | [13 empty] | 26676.42 | 2026-06-09 | 2026 | 6 | 2026-06-18 |  | Y | CO26-034
SGP-033032 | 38914.75 | [13 empty] | 38914.75 | 2026-06-22 | 2026 | 7 | 2026-07-09 |  | Y | CO26-045
SGP-033033 | 95163.17 | [13 empty] | 95163.17 | 2026-06-22 | 2026 | 7 | 2026-07-09 |  | Y | CO26-045
0
0
0
0
0
0
0
0
0
0
0
0

## 2. Syneos
1. CRO:Syneos
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | $ | %
Budget
Paid | 0 | #DIV/0!
Remaining | 0 | #DIV/0!
2.Yearly and Monthly Payment
| USD | KRW
2023 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details | 분기별/연도별 사용 금액 파악위해, 이전 CO Budget만 Quarterly sub-sum으로 입력 (without Invoice/지결 #)
Milestones | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) | Paid (Y) | 지출결의 #

## 3. Sharp
3. Sharp Clinical Services (Including Zuellig Pharma Korea)
| Contract Number: | SLJ221013328 | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on: | 2026-07-23
1. Sub Total Cost Status
Category | $ | %
Budget | 706859
Paid | 581898.39 | 82.32%
Remaining | 124960.61 | 17.68%
2. Yearly and Monthly Payment
2023 | 94935.66 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
2475 | 0 | 9792 | 11106 | 2005 | 3222.47 | 2126.08 | 27227.25 | 16699 | 2393.79 | 14365.67 | 3523.4
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 130398.55 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
1605 | 5917.83 | 0 | 4278.77 | 5386 | 40209.8 | 10282.08 | 20090.3 | 11292.28 | 9961.76 | 21374.73 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 264219.23 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
13016.78 | 10223.34 | 2184.53 | 16658 | 19924.01 | 31779.4 | 30986.18 | 11353.64 | 57782.6 | 39283.52 | 14311.95 | 16715.28
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 92344.95 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
10877.97 | 26519.9 | 11603.99 | 12404.26 | 14311.06 | 12211.97 | 4415.8 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Services | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) | Paid (Y) | 지출결의 #
Project Set-up |  | 1500 | 5200065045 | 2022-12-30 | 2023 | 1 | 2023-01-29 | 0 | Y
Depot Set-up |  | 975 | 5200065045 | 2022-12-30 | 2023 | 1 | 2023-01-29 | 0 | Y
BAL0891 Cam 1: Carton & Vial Labels |  | 1500 | 5200066793 | 2023-02-28 | 2023 | 3 | 2023-03-30 | 0 | Y
BAL0891 Cam 1: Secondary Pacakging |  | 8292 | 5200066793 | 2023-02-28 | 2023 | 3 | 2023-03-30 | 0 | Y
BAL0891 Cam 2: Carton & Vial Labels |  | 1500 | 5200067550 | 2023-03-31 | 2023 | 4 | 2023-04-25 | 0 | Y | CD23-033
BAL0891 Cam 2: Secondary Packaging |  | 8061 | 5200067550 | 2023-03-31 | 2023 | 4 | 2023-04-25 | 0 | Y | CD23-033
BAL0891 Cam 2: Retest Extension Labels KOR |  | 750 | 5200070887 | 2023-07-31 | 2023 | 8 | 2023-08-30 | 0 | Y
BAL0891 Cam 3: Carton & Vial Labels |  | 1500 | 5200070887 | 2023-07-31 | 2023 | 8 | 2023-08-30 | 0 | Y
BAL0891 Cam 3: Secondary Packaging |  | 8292 | 5200071287 | 2023-08-31 | 2023 | 9 | 2023-09-30 | 0 | Y
BAL0891 Cam 3: Retest Extension Labels KOR |  | 1500 | 5200073239 | 2023-10-31 | 2023 | 11 | 2023-11-30 | 0 | Y
BAL0891 Cam 4: Retest Extension Labels US |  | 750 | 5200070887 | 2023-07-31 | 2023 | 8 | 2023-08-30 | 0 | Y
BAL0891 Cam 4: Secondary Packaging |  | 8407 | 5200071287 | 2023-08-31 | 2023 | 9 | 2023-09-30 | 0 | Y
BAL0891 Cam 5: Cartons & Foam Inserts |  | 2220 | 5200077497 | 2024-04-30 | 2024 | 5 | 2024-05-23 | 0 | Y | CD24-100
BAL0891 Cam 5: Carton & Vial Labels |  | 2061 | 5200077547 | 2024-04-30 | 2024 | 5 | 2024-05-23 | 0 | Y | CD24-100
BAL0891 Cam 5: Secondary Packaging |  | 9459 | 5200078686 | 2024-05-30 | 2024 | 6 | 2024-06-20 | 0 | Y | CD24-119
BAL0891 Cam 5: Expiry Extension Labels |  | 3000 | 5200085214 | 2025-05-01 | 2025 | 6 | 2025-06-05 | 0 | Y | CD25-103
BAL0891 Cam 6, 7 & 8: Carton & Foam Insert |  | 6026 | 5200088722 | 2025-04-30 | 2025 | 6 | 2025-06-05 | 0 | Y | CD25-103
BAL0891 Cam 6: PM & Batch Record |  | 3000 | 5200088906 | 2025-04-30 | 2025 | 5 | 2025-05-22 | 0 | Y | CD25-091
BAL0891 Cam 6: Carton & Vial Labels |  | 1575 | 5200089927 | 2025-05-31 | 2025 | 7 | 2025-07-03 | 0 | Y | CD25-121
BAL0891 Cam 6: Secondary Packaging |  | 9455 | 5200092006 | 2025-07-31 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 7: Carton & Vial Labels |  | 2372 | 5200092634 | 2025-08-27 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-175
BAL0891 Cam 7: Secondary Packaging |  | 9862 | 5200092634 | 2025-08-27 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-175
BAL0891 Cam 8: Carton & Vial Labels |  | 2394 | 5200092634 | 2025-08-27 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-175
BAL0891 Cam 8: Secondary Packaging |  | 9897 | 5200092634 | 2025-08-27 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-175
BAL0891 Cam 7,8,9 & 10: Batch Records |  | 2000 | 5200092006 | 2025-07-31 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 7,8,9 & 10: Proejct Management |  | 2000 | 5200092006 | 2025-07-31 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 9: Carton & Vial Labels |  | 3235 | 5200092006 | 2025-07-31 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 9: Carton & Vial Labels (Credit) |  | -3235 | 5200093327 | 2025-09-17 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 9: Carton & Vial Labels |  | 1707 | 5200094062 | 2025-09-30 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 9: Secondary Packaging |  | 9481 | 5200093080 | 2025-08-31 | 2025 | 9 | 2025-09-25 | 0 | Y | CD25-187
BAL0891 Cam 10: Carton & Vial Labels |  | 3040 | 5200092006 | 2025-07-31 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
BAL0891 Cam 10: Secondary Packaging |  | 11652 | 5200093080 | 2025-08-31 | 2025 | 9 | 2025-09-25 | 0 | Y | CD25-187
BAL0891 Cam 9 & 10: Carton & Foam Inserts |  | 8018 | 5200096418 | 2025-12-09 | 2025 | 12 | 2025-12-24 | 0 | Y | CD25-223
BAL0891 Cam 9: Retest Date Extension Labels |  | 1575 | 5200104684 | 2026-06-30 | 2026 | 7 | 2026-07-23 | 0 | Y | CO26-050
Paclitaxel Cam 1: Northstar Drug Procurement |  | 18192 | 5200078157 | 2024-05-21 | 2024 | 6 | 2024-06-13 | 0 | Y | CD24-113
Paclitaxel Cam 1: Carton & Vial Labels US/KOR |  | 1576 | 5200080808 | 2024-07-31 | 2024 | 8 | 2024-08-22 | 0 | Y | CD24-177
Paclitaxel Cam 1: Secondary Packaging US/KOR |  | 16000 | 5200081832 | 2025-05-01 | 2025 | 6 | 2025-06-05 | 0 | Y | CD25-103
Paclitaxel Cam 2: Northstar Drug Procurement |  | 14523 | 5200087108 | 2025-03-20 | 2025 | 4 | 2025-04-03 | 0 | Y | CD25-058
Paclitaxel Cam 2: Secondary Packaging |  | 8000 | 5200089927 | 2025-05-31 | 2025 | 7 | 2025-07-03 | 0 | Y | CD25-121
Paclitaxel Cam 2: Carton & Vial Labels |  | 1575 | 5200089927 | 2025-05-31 | 2025 | 7 | 2025-07-03 | 0 | Y | CD25-121
Paclitaxel Cam 3: Secondary Packaging |  | 8400 | 5200103463 | 2026-05-31 | 2026 | 6 | 2026-06-18 | 0 | Y | CO26-031
Paclitaxel Cam 3: Project Management |  | 2500 | 5200101056 | 2026-03-31 | 2026 | 4 | 2026-04-23 | 0 | Y | CO26-003
Sharp Services: 2022.09 to 2023.02 (Basilea) |  | 24227.25 | 101 299 | 2023-07-12 | 2023 | 8 | 2023-08-11 | 0 | Y
Sharp Services: 2023.03 |  | 1545 | 5200067172 | 2023-03-28 | 2023 | 4 | 2023-04-25 | 0 | Y | CD23-033
Sharp Services: 2023.04 |  | 2005 | 5200068500 | 2023-04-28 | 2023 | 5 | 2023-05-28 | 0 | Y
Sharp Services: 2023.05 |  | 3222.47 | 5200069200 | 2023-05-31 | 2023 | 6 | 2023-06-30 | 0 | Y
Zuellig Services: 2023.05 |  | 4087.2 | 5200070199 | 2024-07-09 | 2025 | 8 | 2025-08-01 | 0 | Y | CD24-159
Sharp Services: 2023.06 |  | 2784 | 5200070171 | 2024-07-09 | 2024 | 8 | 2024-08-01 | 0 | Y | CD24-156
Zuellig Services: 2023.06 |  | 3942.4 | 5200079105 | 2024-06-13 | 2024 | 7 | 2024-07-13 | 0 | Y
Zuellig Services: 2023.06 (Credit) |  | -806 | 5200075835 | 2024-02-27 | 2024 | 7 | 2024-07-13 | 0 | Y
Sharp Services: 2023.07 |  | 2126.08 | 5200070877 | 2023-07-01 | 2023 | 7 | 2023-07-31 | 0 | Y
Zuellig Services: 2023.07 |  | 873.6 | 5200072442 | 2023-10-12 | 2023 | 11 | 2023-11-11 | 0 | Y
Sharp Services: 2023.08 |  | 2393.79 | 5200071638 | 2023-09-14 | 2023 | 10 | 2023-10-14 | 0 | Y
Zuellig Services: 2023.08 |  | 873.6 | 5200072441 | 2023-10-12 | 2023 | 11 | 2023-11-11 | 0 | Y
Sharp Services: 2023.09 |  | 5589.27 | 5200072333 | 2023-10-09 | 2023 | 11 | 2023-11-08 | 0 | Y
Zuellig Services: 2023.09 |  | 4202.2 | 5200072541 | 2023-10-23 | 2023 | 11 | 2023-11-22 | 0 | Y
Sharp Services: 2023.10 |  | 1327 | 5200073166 | 2023-10-27 | 2023 | 11 | 2023-11-26 | 0 | Y
Zuellig Services: 2023.10 |  | 2418.4 | 5200073887 | 2023-11-30 | 2023 | 12 | 2023-12-30 | 0 | Y
Sharp Services: 2023.11 |  | 1105 | 5200074050 | 2023-11-30 | 2023 | 12 | 2023-12-30 | 0 | Y
Zuellig Services: 2023.11 |  | 1882.8 | 5200074353 | 2023-12-27 | 2024 | 2 | 2024-02-08 | 0 | Y | CD24-024
Sharp Services: 2023.12 |  | 1605 | 5200074453 | 2023-12-27 | 2024 | 1 | 2024-01-18 | 0 | Y | CD24-010
Zuellig Services: 2023.12 |  | 1882.8 | 5200075141 | 2024-01-23 | 2024 | 2 | 2024-02-08 | 0 | Y | CD24-024
Sharp Services: 2024.01 |  | 1501.88 | 5200075740 | 2024-02-01 | 2024 | 2 | 2024-02-22 | 0 | Y | CD24-043
Sharp Services: 2024.01 (PM & Freight) |  | 650.35 | 5200075741 | 2024-02-02 | 2024 | 2 | 2024-02-22 | 0 | Y | CD24-043
Zuellig Services: 2024.01 |  | 1258.4 | 5200076555 | 2024-03-25 | 2024 | 4 | 2024-04-18 | 0 | Y | CD24-078
Sharp Services: 2024.02 |  | 3020.37 | 5200076461 | 2024-03-14 | 2024 | 4 | 2024-04-04 | 0 | Y | CD24-069
Sharp Services: 2024.02 (PM) |  | 500 | 5200078947 | 2024-06-10 | 2024 | 7 | 2024-07-04 | 0 | Y | CD24-130
Zuellig Services: 2024.02 |  | 6844.4 | 5200078052 | 2024-05-15 | 2024 | 10 | 2024-10-10 | 0 | Y | CD24-211
Sharp Services: 2024.03 |  | 1105 | 5200077260 | 2024-04-15 | 2024 | 5 | 2024-05-23 | 0 | Y | CD24-100
Zuellig Services: 2024.03 |  | 8758.8 | 5200078171 | 2024-05-24 | 2024 | 6 | 2024-06-20 | 0 | Y | CD24-126
Sharp Services: 2024.04 |  | 3800 | 5200078006 | 2024-05-10 | 2024 | 6 | 2024-06-13 | 0 | Y | CD24-113
Zuellig Services: 2024.04 |  | 5274 | 5200078172 | 2024-05-24 | 2024 | 9 | 2024-09-05 | 0 | Y | CD24-189
Zuellig Services: 2024.04 (Credit) |  | -1560 | 5200081129 | 2024-08-19 | 2024 | 9 | 2024-09-05 | 0 | Y | CD24-189
Sharp Services: 2024.05 |  | 1590 | 5200078746 | 2024-05-30 | 2024 | 7 | 2024-07-04 | 0 | Y | CD24-135
Sharp Services: 2024.06 |  | 5055.68 | 5200079921 | 2024-07-09 | 2024 | 7 | 2024-07-18 | 0 | Y | CD24-151
Zuellig Services: 2024.05 & 2024.06 |  | 13444.8 | 5200080497 | 2024-07-30 | 2024 | 8 | 2024-08-22 | 0 | Y | CD24-178
Sharp Services: 2024.07 |  | 2285.5 | 5200080874 | 2024-08-06 | 2024 | 8 | 2024-08-22 | 0 | Y | CD24-175
Zuellig Services: 2024.07 |  | 3620.4 | 5200081714 | 2024-08-30 | 2024 | 9 | 2024-09-26 | 0 | Y | CD24-202
Sharp Services: 2024.08 |  | 3957.88 | 5200081299 | 2024-08-23 | 2024 | 9 | 2024-09-12 | 0 | Y | CD24-192
Zuellig Services: 2024.08 |  | 13239.6 | 5200082795 | 2024-10-09 | 2024 | 11 | 2024-11-21 | 0 | Y | CD24-239
Sharp Services: 2024.09 |  | 3117.36 | 5200082682 | 2024-10-02 | 2024 | 10 | 2024-10-24 | 0 | Y | CD24-212
Zuellig Services: 2024.09 |  | 2329.6 | 5200083437 | 2024-10-31 | 2024 | 11 | 2024-11-21 | 0 | Y | CD24-243
Sharp Services: 2024.10 |  | 5805.53 | 5200083043 | 2024-10-24 | 2024 | 11 | 2024-11-21 | 0 | Y | CD24-239
Zuellig Services: 2024.10 |  | 7602.5 | 5200083925 | 2024-11-22 | 2025 | 1 | 2025-01-16 | 0 | Y | CD25-001
Sharp Services: 2024.11 |  | 2900.36 | 5200084578 | 2024-12-17 | 2025 | 1 | 2025-01-02 | 0 | Y | CD24-284
Zuellig Services: 2024.11 |  | 2185.5 | 5200084886 | 2024-12-30 | 2025 | 2 | 2025-02-06 | 0 | Y | CD25-019
Sharp Services: 2024.12 |  | 2513.92 | 5200085157 | 2024-12-30 | 2025 | 1 | 2025-01-16 | 0 | Y | CD25-009
Zuellig Services: 2024.12 |  | 5363.5 | 5200085928 | 2025-01-30 | 2025 | 2 | 2025-02-20 | 0 | Y | CD25-028
Sharp Services: 2025.01 |  | 2674.34 | 5200086152 | 2025-02-10 | 2025 | 2 | 2025-02-20 | 0 | Y | CD25-030
Zuellig Services: 2025.01 |  | 4189.5 | 5200087679 | 2025-03-31 | 2025 | 5 | 2025-05-22 | 0 | Y | CD25-083
Sharp Services: 2025.02 |  | 2184.53 | 5200086867 | 2025-03-10 | 2025 | 3 | 2025-03-20 | 0 | Y | CD25-047
Zuellig Services: 2025.02 |  | 8979.8 | 5200088531 | 2025-04-29 | 2025 | 5 | 2025-05-22 | 0 | Y | CD25-091
Sharp Services: 2025.03 |  | 2135 | 5200087800 | 2025-03-31 | 2025 | 4 | 2025-04-17 | 0 | Y | CD25-065
Zuellig Services: 2025.03 |  | 6753.4 | 5200089294 | 2025-05-20 | 2025 | 6 | 2025-06-19 | 0 | Y | CD25-114
Sharp Services: 2025.04 |  | 3754.71 | 5200089005 | 2025-05-06 | 2025 | 5 | 2025-05-22 | 0 | Y | CD25-091
Zuellig Services: 2025.04 |  | 12952.2 | 5200090391 | 2025-06-24 | 2025 | 7 | 2025-07-31 | 0 | Y | CD25-142
Sharp Services: 2025.05 |  | 4132.56 | 5200089619 | 2025-05-28 | 2025 | 7 | 2025-07-03 | 0 | Y | CD25-121
Zuellig Services: 2025.05 |  | 2826.6 | 5200091728 | 2025-07-31 | 2025 | 8 | 2025-08-28 | 0 | Y | CD25-159
Sharp Services: 2025.06 |  | 2751.42 | 5200090833 | 2025-07-07 | 2025 | 7 | 2025-07-31 | 0 | Y | CD25-142
Zuellig Services: 2025.06 |  | 4472.8 | 5200092328 | 2025-08-18 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-176
Sharp Services: 2025.07 |  | 4439.84 | 5200091989 | 2025-07-31 | 2025 | 8 | 2025-08-28 | 0 | Y | CD25-159
Zuellig Services: 2025.07 |  | 3743.3 | 5200092403 | 2025-08-18 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-176
Zuellig Services: 2025.08 |  | 13710.5 | 5200093742 | 2025-09-29 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
Sharp Services: 2025.08 |  | 3908.5 | 5200092979 | 2025-08-28 | 2025 | 9 | 2025-09-11 | 0 | Y | CD25-176
Sharp Services: 2025.09 |  | 7371.02 | 5200093853 | 2025-09-30 | 2025 | 10 | 2025-10-30 | 0 | Y | CD25-197
Zuellig Services: 2025.09 |  | 9419.5 | 5200094602 | 2025-10-27 | 2025 | 11 | 2025-11-27 | 0 | Y
Sharp Services: 2025.10 |  | 4892.45 | 5200094778 | 2025-10-28 | 2025 | 11 | 2025-11-27 | 0 | Y
Zuellig Services: 2025.10 |  | 5675.5 | 5200095880 | 2025-11-29 | 2025 | 12 | 2025-12-24 | 0 | Y | CD25-224
Sharp Services: 2025.11 |  | 3021.78 | 5200095885 | 2025-11-29 | 2025 | 12 | 2025-12-24 | 0 | Y | CD25-224
Zuellig Services: 2025.11 |  | 5935.5 | 5200097072 | 2025-12-29 | 2026 | 1 | 2026-01-22 | 0 | Y | CD26-006
Sharp Services: 2025.12 |  | 4942.47 | 5200097162 | 2025-12-23 | 2026 | 1 | 2026-01-22 | 0 | Y | CD26-006
Zuellig Services: 2025.12 |  | 23296.5 | 5200098538 | 2026-01-30 | 2026 | 2 | 2026-02-26 | 0 | Y | CD26-015
Sharp Services: 2026.01 |  | 3223.4 | 5200098613 | 2026-02-02 | 2026 | 2 | 2026-02-26 | 0 | Y | CD26-015
Zuellig Services: 2026.01 |  | 7677.5 | 5200099630 | 2026-02-27 | 2026 | 3 | 2026-03-26 | 0 | Y | CD26-032
Sharp Services: 2026.02 |  | 3926.49 | 5200099562 | 2026-02-26 | 2026 | 3 | 2026-03-26 | 0 | Y | CD26-032
Zuellig Services: 2026.02 |  | 5667.3 | 5200100787 | 2026-03-27 | 2026 | 4 | 2026-04-09 | 0 | Y | CD26-042
Sharp Services: 2026.03 |  | 4236.96 | 5200100650 | 2026-03-24 | 2026 | 4 | 2026-04-09 | 0 | Y | CD26-042
Sharp Services: LPM (2026.01 ~ 2026.04) |  | 2000 | 5200102042 | 2026-04-29 | 2026 | 5 | 2026-05-21 | 0 | Y | CO26-010
Paclitaxel Cam 3: Batch Record |  | 2075 | 5200102254 | 2026-04-30 | 2026 | 5 | 2026-05-21 | 0 | Y | CO26-010
Zuellig Services: 2026.03 |  | 5944.4 | 5200101636 | 2026-04-21 | 2026 | 5 | 2026-05-21 | 0 | Y | CO26-016
Sharp Services: 2026.04 |  | 4291.66 | 5200102384 | 2026-05-06 | 2026 | 5 | 2026-05-21 | 0 | Y | CO26-016
Zuellig Services: 2026.04 |  | 1840.8 | 5200103157 | 2026-05-28 | 2026 | 7 | 2026-07-09 | 0 | Y | CO26-036
Sharp Services: 2026.05 |  | 3811.97 | 5200102957 | 2026-05-26 | 2026 | 6 | 2026-06-18 | 0 | Y | CO26-031
Sharp Services: LPM (2026.05) |  | 500 | 5200103033 | 2026-05-26 | 2026 | 7 | 2026-07-09 | 0 | Y | CO26-036
Zuellig Services: 2026.05 |  | 10151.4 | 5200104377 | 2026-07-22 | 2026 | 8 |  | 0
Sharp Services: LPM (2026.06) |  | 500 | 5200104078 | 2026-06-17 | 2026 | 7 | 2026-07-23 | 0 | Y | CO26-049
Sharp Services: 2026.06 |  | 3156.14 | 5200104883 | 2026-07-10 | 2026 | 8 |  | 0
Total | 706859 | 595205.93

## 4. Fisher
4. Fisher Clinical Services (KOR & US Mt Prospect)
| Contract Number: | PSG-A-1106216 | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on: | 2026-07-23
1. Sub Total Cost Status
Category | ₩ | %
Budget | 249693702
Paid | 82331344 | 32.97%
Remaining | 167362358 | 67.03%
2. Yearly and Monthly Payment
2025 | 0 | 15142569
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4838959 | 3344264 | 3663082 | 3296264
2026 | 0 | 67188775
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30552133 | 2499191 | 14479210 | 5197074 | 4006625 | 4954690 | 5499852 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Services | Budget Amount(₩) | Invoiced Amount(₩) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Amount(₩) | VAT(₩) | Total Amount(₩) | Paid (Y) | 지출결의 #
Study Set-up (KOR) |  |  | 7316 | 2025-08-24 | 2025 | 9 | 2025-09-18 | 3620223 | 362023 | 3982246 | Y | CD25-183
Fisher Clinical Services (KOR): 2025.08 (PM) |  |  | 7316 | 2025-08-24 | 2025 | 9 | 2025-09-18 | 1218736 | 121873 | 1340609 | Y | CD25-183
Fisher Clinical Services (KOR): 2025.09 |  |  | 7443 | 2025-09-23 | 2025 | 10 | 2025-10-16 | 3344264 | 334426 | 3678690 | Y | CD25-192
Fisher Clinical Services (KOR): 2025.10 |  |  | 7590 | 2025-10-24 | 2025 | 11 | 2025-11-13 | 3663082 | 366308 | 4029390 | Y | CD25-200
Fisher Clinical Services (KOR): 2025.11 |  |  | 7718 | 2025-11-24 | 2025 | 12 | 2025-12-04 | 3296264 | 329626 | 3625890 | Y | CD25-213
Fisher Clinical Services(KOR): 2025.12 + Tislelizumab 1st Campaign (US&KOR) |  |  | 7867 | 2025-12-22 | 2026 | 1 | 2026-01-15 | 30552133 | 3055213 | 33607346 | Y | CD26-003
Fisher Clinical Services (KOR): 2026.01 |  |  | 8020 | 2026-01-23 | 2026 | 2 | 2026-02-05 | 2499191 | 249919 | 2749110 | Y | CD26-013
Study Set-up (US) |  |  | 8231 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 4655550 | 465555 | 5121105 | Y | CD26-028
Fisher Clinical Services (US): 2025.12 |  |  | 8232 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 1131752 | 113175 | 1244927 | Y | CD26-028
Fisher Clinical Services (US): 2026.12 (Storage) |  |  | 8233 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 361870 | 36187 | 398057 | Y | CD26-028
Fisher Clinical Services (US): 2026.01 (Storage) |  |  | 8234 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 361870 | 36187 | 398057 | Y | CD26-028
Fisher Clinical Services (KOR): 2026.02 |  |  | 8180 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 6195043 | 619504 | 6814547 | Y | CD26-028
Fisher Clinical Services (US): 2026.01 |  |  | 8235 | 2026-02-22 | 2026 | 3 | 2026-03-12 | 1773125 | 177313 | 1950438 | Y | CD26-028
Fisher Clinical Services (US): 2026.02 |  |  | 8392 | 2026-03-22 | 2026 | 4 | 2026-04-16 | 1131409 | 113141 | 1244550 | Y | CD26-046
Fisher Clinical Services (US): 2026.02 (Storage) |  |  | 8391 | 2026-03-22 | 2026 | 4 | 2026-04-16 | 723739 | 72374 | 796113 | Y | CD26-046
Fisher Clinical Services (KOR): 2026.03 |  |  | 8390 | 2026-03-22 | 2026 | 4 | 2026-04-16 | 3341926 | 334193 | 3676119 | Y | CD26-046
Fisher Clinical Services (US): 2026.04 |  |  | 8440 | 2026-04-26 | 2026 | 5 | 2026-05-07 | 1773125 | 177313 | 1950438 | Y | CO26-007
Fisher Clinical Services (US): 2026.04 (Storage) |  |  | 8441 | 2026-04-26 |  |  |  | 361870 |  | 361870 | N
Fisher Clinical Services (US): 2026.03 (Storage) - Credit for 8391 |  |  | 4079761C | 2026-05-12 |  |  |  | -361870 |  | -361870 | N
Fisher Clinical Services (KOR): 2026.04 |  |  | 8439 | 2026-04-26 | 2026 | 5 | 2026-05-07 | 2233500 | 223350 | 2456850 | Y | CO26-007
Fisher Clinical Services (KOR): 2026.05 |  |  | 8677 | 2026-05-26 | 2026 | 6 | 2026-06-11 | 4465320 | 446532 | 4911852 | Y | CO26-026
Fisher Clinical Services (US): 2026.04 (Storage) |  |  | 8678 | 2026-05-25 | 2026 | 6 | 2026-06-11 | 361870 | 36187 | 398057 | Y | CO26-026
Fisher Clinical Services (US): 2026.04 (Freight) |  |  | 8679 | 2026-05-26 | 2026 | 6 | 2026-06-11 | 127500 | 12750 | 140250 | Y | CO26-026
Fisher Clinical Services (KOR): 2026.06 |  |  | 9214 | 2026-06-21 | 2026 | 7 | 2026-07-09 | 2233500 | 223350 | 2456850 | Y | CO26-042
Fisher Clinical Services (US): 2026.05 |  |  | 92141 | 2026-06-21 | 2026 | 7 | 2026-07-09 | 2904482 | 290448 | 3194930 | Y | CO26-042
Fisher Clinical Services (US): 2026.05 (Storage) |  |  | 92142 | 2026-06-21 | 2026 | 7 | 2026-07-09 | 361870 | 36187 | 398057 | Y | CO26-042
Total | 249693702 | 0

## 5. Marken
5. Marken
| Contract Number: |  | Version & date: | CO1_23Sep2025
Protocol No: TTK-CS-101 |  |  | Updated on: | 2026-07-23
1. Sub Total Cost Status
Category | ₩ | %
Budget | 149805492
Paid | 149805492 | 100%
Remaining | 0 | 0%
2. Yearly and Monthly Payment
2023 | 0 | 6874940
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 6832940 | 0 | 42000 | 0 | 0 | 0 | 0
2024 | 0 | 39872732
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 29201942 | 0 | 0 | 0 | 10670790 | 0 | 0
2025 | 0 | 85621177
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 2942881 | 0 | 34675243 | 5119000 | 42884053 | 0 | 0
2026 | 0 | 17436643
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11907417 | 0 | 0 | 0 | 0 | 0 | 0 | 5529226 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Services | Budget Amount(₩) | Invoiced Amount(₩) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Transport Amount(₩) | Duty & Tax(₩) | Total Amount(₩) | Paid (Y) | 지출결의 #
BAL0891 Internal Standard Shipment: 10mg (Eurofins:Germany to SBQ:Swiss) | 976003 |  | SEL13786 | 2023-04-27 | 2023 | 5 | 2023-05-25 | 976003 | 0 | 976003 | Y | CO23-060
BAL0891 IP 1st Shipment: 50 Kits (Sharp:US to Zuellig:KOR) | 3450500 |  | SEL14022 | 2023-05-23 | 2023 | 6 | 2023-06-15 | 2876650 | 573850 | 3450500 | Y | CO23-082
BAL0891 IP 2nd Shipment: 50 Kits (Sharp:US to Zuellig:KOR) | 3382440 |  | SEL14235 | 2023-06-14 | 2023 | 6 | 2023-06-29 | 2803150 | 579290 | 3382440 | Y | CO23-103
BAL0891 IP 2nd Shipment: US Export Declaration Fee | 42000 |  | SEL14826 | 2023-08-21 | 2023 | 8 | 2023-08-31 | 0 | 42000 | 42000 | Y | CO23-158
BAL0891 IP 3rd Shipment: 90 Kits (Sharp:US to Zuellig:KOR) | 6793120 |  | SEL15057 | 2023-09-15 | 2025 | 10 | 2025-10-12 | 4867810 | 1925310 | 6793120 | Y | CO23-182
BAL0891 IP 4th Shipment: 90 Kits (Sharp:US to Zuellig:KOR) | 5343625 |  | SEL15197 | 2023-10-05 | 2025 | 10 | 2025-10-26 | 4311805 | 1031820 | 5343625 | Y | CO23-196
BAL0891 IP 5th Shipment: 891 Kits (Sharp:US to Zuellig:KOR) | 29201942 |  | SEL17590 | 2024-06-10 | 2024 | 6 | 2024-06-27 | 18992332 | 10209610 | 29201942 | Y | CO24-105
Paclitaxel IP 1st Shipment: 254 Kits (Sharp:US to Zuellig:KOR) | 10670790 |  | SEL18511 | 2024-09-23 | 2024 | 10 | 2024-10-10 | 7050800 | 3619990 | 10670790 | Y | CO24-185
BAL0891 IP Internal Standard Shipment: 10mg (Eurofins:Germany to SBQ:KOR) | 2942881 |  | SEL21038 | 2025-06-09 | 2025 | 6 | 2025-06-26 | 2529911 | 412970 | 2942881 | Y | CO25-113
BAL0891 IP 6th Shipment: 998 Kits (Sharp:US to Zuellig:KOR) | 34675243 |  | SEL21663 | 2025-08-11 | 2025 | 8 | 2025-08-28 | 21798633 | 12876610 | 34675243 | Y | CO25-169
BAL0891 IP Shipment: 300 kits (Sharp:US to Piramal:US) | 5119000 |  | SEL21868 | 2025-08-21 | 2025 | 9 | 2025-09-04 | 5119000 | 0 | 5119000 | Y | CO25-174
BAL0891 IP 7th Shipment: 698 Kits (Sharp:US to Zuellig:KOR) | 22264275 |  | SEL22347 | 2025-10-02 | 2025 | 10 | 2025-10-30 | 13268835 | 8995440 | 22264275 | Y | CO25-211
Tislelizumab IP 1st Supply: 300 Vials (Beigene:CHINA to FCS:KOR) | 8483033 |  | SEL22348 | 2025-10-02 | 2025 | 10 | 2025-10-30 | 4751933 | 3731100 | 8483033 | Y | CO25-211
Tislelizumab IP 1st Shipment: 149 Kits (FCS Korea to FCS US) | 11907417 |  | SEL23563 | 2026-01-09 | 2026 | 1 | 2026-01-29 | 10158008 | 1749409 | 11907417 | Y | CO126-005
Paclitaxel IP 2nd Shipment: 35 Kits (Sharp:US to Zuellig:KOR) | 5529226 |  | SEL25960 | 2026-07-16 | 2026 | 8 | 2026-08-06 | 4353686 | 1175540 | 5529226 | Y | CO26-057
Total | 149805492 | 0

## 6. SBQ
4. SBQ
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | CHF | %
Budget | 440404.83
Paid | 160795.18 | 36.51%
Remaining | 279609.65 | 63.49%
2. Yearly and Monthly Payment
| CHF | KRW
2023 | 69301.98 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 67333.98 | 0 | 0 | 0 | 0 | 0 | 1968 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2024 | 4750 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4750
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025 | 76627.2 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
6213.6 | 0 | 0 | 70413.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 10116 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 10116 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Quotation details
Quotation Date | Quote No. | Contracted | Total Quotation Amount | Payment milestone | Invoice amount to be billed | Issued invoice # | Paid | Paid Year | Paid Month | Payment Date | Invoiced Amount(CHF) | Total Amount(₩) | 지출결의 # | Remarks
2022.11.30 | Q210126 | Y (2023.01.12) | 202800 | 30% after giving the order | 60840 | 230046-1 | Y | 2023 | 02 | 2023-02-23 | 60840
|  |  |  | 50% after delivery of the results | 101400 | 230046-2 | Y | 2025 | 04 | 2025-04-30 | 50700 |  |  | They billed us 50700 but this amount is not in the contract nor can be confirmed. | 계약서와 내용이 다름 + Delivery Result에 대한 Define이 되어야 한다. 우리도 invoice를 처리하기 위해서 지금 문의를 하고 있는 것이다.
|  |  |  | 20% after delivery of the final draft study report | 40560
2025.03.20 | Q210126_Amd01 | Y (2026.03.11) | 235300 | 30% after giving the order | 70590
|  |  |  | 50% after delivery of the results | 117650
|  |  |  | 20% after delivery of the final draft study report | 47060
2022.12.20 | Q210466 | Y (2023.01.12) | 12987.95 | 50% after giving the order | 6493.98 | 220327-1 | Y | 2023 | 02 | 2023-02-23 | 6493.98
|  |  |  | 50% after delivery of kits | 6493.98
2024.08.09 | Q210466 | N | 12987.95 | 50% after giving the order | 6493.98
|  |  |  | 50% after delivery of kits | 6493.98 | 220327-2 | Y |  |  |  | 39245.88 |  |  | They billed us 39245.88 this was 57.47% of the total amount but there was no reference and no contract was made. (Based on Quotation dated 2024.08.09). | 이거는 서명이 된 Quote가 아니고, 새롭게 지금 전달 해준 2025 3월에 준 Quotation을 기반으로 서명하고,
2025.03.20 | Q210466_Amd01 | N | 69062.89 | 50% after giving the order | 34531.45
|  |  |  | 50% after delivery of kits | 34531.45
2024.09.30 | Q220591_Amd01 | N | 14500 | 50% after giving the order | 7250 | 240154-F | Y |  |  |  | 7250 |  |  | This was invoiced for the provided interim analysis but the quotation was not signed and contract amendment was ongoing. No communication email since it was not contracted.
|  |  |  | 50% after delivery of the final draft study report | 7250 | 240154-F | Y |  |  |  | 7250
2023.06.16 | Q230208 | Y (2023.06.20) | 3936 | 50% after giving the order | 1968 | 230187-1 | Y | 2023 | 08 | 2023-08-10 | 1968
|  |  |  | 50% after storage period (1 year) | 1968 | 230187-2 | Y | 2026 | 05 | 2026-05-21 | 1968 |  |  |  | invoice 발행을 해주면 지급하겠다고 전달.
[5 empty] | 3456 | 230187-3 | Y | 2026 | 05 | 2026-05-21 | 3456
[5 empty] | 4692 | 230187-4 | Y | 2026 | 05 | 2026-05-21 | 4692
2023.12.22 | Q230464 | Y (2024.01.24) | 6213.6 | 50% after giving the order | 3106.8 | 240218-F | Y | 2025 | 04 | 2025-04-30 | 3106.8 |  |  | This was not paid since no inventory log was provided but as we not have the actual inventory log obtained, it can be paid. | 바로 지급 진행
|  |  |  | 50% after completion of the study | 3106.8 | 240218-F | Y | 2025 | 04 | 2025-04-30 | 3106.8 |  |  | This was not paid since no inventory log was provided but as we not have the actual inventory log obtained, it can be paid. | 바로 지급 진행
2024.04.29 | Q240152 | Y (2023.06.13) | 4750 | 50% after giving the order | 2375 | 240156-F | Y | 2024 | 12 | 2024-12-05 | 2375
|  |  |  | 50% after delivery of the final draft study report | 2375 | 240156-F | Y | 2024 | 12 | 2024-12-05 | 2375
2024.08.06 | Q240254 | Y (2024.10.14) | 45000 | 30% after giving the order | 13500 | 240221-1 | Y | 2025 | 04 | 2025-04-30 | 13500 |  |  | They increase the report cost to 2000 to 2500 and invoiced 13650 which is not contracted. No email communication as this was during the amendment. | Invioice 수정 요청 진행 하고, 지급 할 수 있도록 처리 할 예정이다.
|  |  |  | 50% after delivery of the results | 22500
|  |  |  | 20% after delivery of the final draft study report | 9000
2025.03.20 | Q240256 | N | 40863.14 | 50% after giving the order | 20431.57 | [9 empty] | Actual Cost를 확인 해야 한다는 의도가 잘못 전달이 된 것 같다 -> Actual cost를 기반으로 해서 청구를 한다는 것을 아래의 Email에서 Confirm을 해주었기 때문에, 해당 내용을 기반으로 Quotation 진행 하겠다. Quote 부터 진행하고 그 뒤에 invoice 청구를 해달라.
|  |  |  | 50% after delivery of kits | 20431.57
2025.03.20 | Q250120 | Y (2025.05.08) | 6213.6 | 100% after giving the order | 6213.6 | 250009-F | Y | 2025 | 01 | 2025-01-02 | 6213.6
2025.03.20 | Q250122 | N | 14565.6 | 100% after giving the order | 14565.6
[10 empty] | Total Amount Paid | 204425.06 |  |  | 347522602
[10 empty] | To Payout now |  |  |  | -
[10 empty] | Total Contracted (to be contracted Amount) | 440404.83 |  |  | 748688211
[10 empty] | To be Paid | 235979.77 |  |  | 401165609 | 지금까지 사용 한 비용 정리해서 업데이트
* 전임자 작성 내용; Further FU 필요

## 7. Aptamer
5. Aptamer
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | ₩ | %
Budget | 294600000
Paid | 54450000 | 18.48%
Remaining | 240150000 | 81.52%
2. Yearly and Monthly Payment
KRW
2025 | 54450000
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 14190000 | 0 | 0 | 0 | 0 | 28380000 | 11880000
2026 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Study 분류 | CTA# | Milestones | Budget Amount(₩) VAT제외 | Invoiced Amount(₩) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) VAT 포함 | Paid (Y) | 지출결의 #
SS4 | CLA25028_20250430 | CTA FE | 12900000 | 12900000 |  | 2025-06-11 | 2025 | 6 | 26 | 14190000 | Y | CO25-127
| CLA25028_20250430 | 시료분석 개시 후 | 25800000 | 25800000 |  | 2025-11-17 | 2025 | 11 | 27 | 28380000 | Y | CO125-004
| CLA25028_20250430 | 계약 시료수 50% 이상 분석 | 25800000
| CLA25028_20250430 | 의뢰사의 보고서 초안 수령 | 25800000
| CLA25028_20250430 | 의뢰사의 최종 결과 보고서 승인 | 38700000
| CLA25028_20250430 | site의 sampling kit 수령 확인 | 6138000
| CLA25028_20250430 | 각 이송건의 검체 수령 확인 | 105462000
SS2 | CLA25085_20251124 | CTA FE | 10800000 | 10800000 |  | 2025-12-12 | 2025 | 12 | 18 | 11880000 | Y | CO125-023
| CLA25085_20251124 | Sample analysis protocol 승인 | 8100000
| CLA25085_20251124 | 시료분석 개시 | 8100000
| CLA25085_20251124 | 시료분석 완료 | 16200000
| CLA25085_20251124 | 의뢰사의 최종 결과 보고서 승인 | 10800000
|  | Total | 294600000

## 8. Invivo
6. Invivo
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | $ | %
Budget | 490894
Paid | 213142.36 | 43.42%
Remaining | 277751.64 | 56.58%
2. Yearly and Monthly Payment
| USD | KRW
2025 | 184437.87 | 184330.91
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 162651 | 4038 | 9255.57 | 4317.74 | 4175.56
0 | 0 | 0 | 0 | 0 | 0 | 0 | 162651 | 4038 | 9148.61 | 4317.74 | 4175.56
2026 | 28704.49 | 28704.49
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
4512.03 | 0 | 8972.12 | 6668.66 | 4148 | 4403.68 | 0 | 0 | 0 | 0 | 0 | 0
4512.03 | 0 | 8972.12 | 6668.66 | 4148 | 4403.68 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Service Deliverables | Milestones | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount($) | Paid (Y) | 지출결의 #
Study setup fee | Upfront fee due upon WO effective date (non-refundable) | 25000 | 162651 | 110007019 | 2025-06-30 | 2025 | 8 | 14 | 162651 | Y | CD25-153
Data Management Fee |  | 25000 | 4038 | 110007238 | 2025-07-31 | 2025 | 9 | 11 | 4038 | Y | CD25-173
Collection Kits |  | 12000 | 4796.15 | 110007486 | 2025-08-31 | 2025 | 10 | 30 | 4689.19 | Y | CD25-194
25% of the Testing Services |  | 92575 | 4459.42 | 110007719 | 2025-09-30 | 2025 | 10 | 30 | 4459.42 | Y | CD25-194
Project Management Fee (13 months) | $4,038, Monthly for 13 months | 52494 | 4317.74 | 110007978 | 2025-10-31 | 2025 | 11 | 27 | 4317.74 | Y | CD25-208
75% of the Testing Services | Monthly, based on the # of samples tested and reported during that month | 277725 | 4175.56 | 110008236 | 2025-11-30 | 2025 | 12 | 24 | 4175.56 | Y | CD25-226
Storage Fee | Monthly | 4550 | 4512.03 | 110008460 | 2025-12-31 | 2026 | 1 | 22 | 4512.03 | Y | CD26-005
Disposition/Shipment Base Fee | Upon disposition/transfer | 500 | 4246.09 | 110008812 | 2026-01-31 | 2026 | 3 | 26 | 4246.09 | Y | CD26-035
Disposition/Shipment Per Sample Fee | Upon disposition/transfer ($15) | 1050 | 4726.03 | 110009031 | 2026-02-28 | 2026 | 3 | 26 | 4726.03 | Y | CD26-037
Pass-through expenses | To be billed as incurred |  | 6668.66 | 110009327 | 2026-03-31 | 2026 | 4 | 23 | 6668.66 | Y | CD26-049
Storage Fee | Monthly |  | 4148 | 110009659 | 2026-04-30 | 2026 | 5 | 21 | 4148 | Y | CO26-018
Storage Fee | Monthly |  | 4403.68 | 110009972 | 2026-05-31 | 2026 | 6 | 18 | 4403.68 | Y | CO26-033
Storage Fee | Monthly |  | 4421.08 | 110010223 | 2026-06-30 | 2026
| Total | 490894

## 9. Labconnect
9. LabConnect
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | $ | %
Budget | 68277
Paid | 45962.23 | 67.32%
Remaining | 22314.77 | 32.68%
2. Yearly and Monthly Payment
| USD | KRW
2025 | 45962.23 | 45962.26
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45130 | 0 | 0 | 832.23
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45130 | 0 | 0 | 832.26
2026 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Contract # |  |  | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) | Paid (Y) | 지출결의 #
SLJNS101_ver.4.0 | Advance Payment | Project Initiation, non-refundable | 14530 | 45130 | SI145264 | 2025-08-20 | 2025 | 9 | 11 | 45130 | Y | CD25-182
SLJNS101_ver.4.0 |  | Expedited Startup, non-refundable | 18900 | 832.23 | SI146666 | 2025-11-18 | 2025 | 12 | 11 | 832.26 | Y | CD25-214
SLJNS101_ver.4.0 |  | Project Deposit (will be credited to final invoices) | 13655
SLJNS101_ver.4.0 | Maintenance | Project Management | 11700
SLJNS101_ver.4.0 |  | Supplies | 22240
SLJNS101_ver.4.0 |  | Logistics | 4275
SLJNS101_ver.4.0 | Discount & Credit | Discount | -3368
SLJNS101_ver.4.0 |  | To be credited to final invoices | -13655
|  | Total | 68277

## 10. AIMS
7. AIMS
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | ₩ | %
Budget | 367130000
Paid | 250597600 | 68.26%
Remaining | 116532400 | 31.74%
2. Yearly and Monthly Payment
KRW
2023 | 23650000
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23650000 | 0 | 0
2024 | 100094500
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 37620000 | 0 | 15779500 | 37620000 | 9075000 | 0
2025 | 117877100
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
50160000 | 0 | 0 | 23650000 | 0 | 0 | 0 | 0 | 0 | 0 | 19212600 | 24854500
2026 | 8976000
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 8976000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Contract # | Milestones | Budget Amount(₩) VAT제외 | Invoiced Amount(₩) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(₩) VAT 포함 | Paid (Y) | 지출결의 #
AIMS-SA-033.v4_20231006 | CTA FE | 21500000 | 23650000 | 23SLJ01-01 | 2023-10-10 | 2023 | 10 | 2023-10-19 | 23650000 | Y | CO23-198
AIMS-SA-033.v4_20231006 | 업무 완료 | 21500000 | 23650000 | 23SLJ01-01 | 2025-03-07 | 2025 | 4 | 2025-04-17 | 23650000 | Y | CO25-067
AIMS-SA-033.v4_20240626 | CTA FE | 34200000 | 37620000 | 23SLJ01-03 | 2024-06-28 | 2024 | 7 | 2024-07-11 | 37620000 | Y | CO24-123
AIMS-SA-033.v4_20240626 | 성과물 전달 | 34200000 | 37620000 | 23SLJ01-03 | 2024-09-26 | 2024 | 10 | 2024-10-10 | 37620000 | Y | CO24-190
AIMS-SA-033.v4_20240626 | 업무 완료 | 45600000 | 50160000 | 23SLJ01-03 | 2025-01-15 | 2025 | 1 | 2025-01-23 | 50160000 | Y | CO25-014
AIMS-SA-033.v4_20240909 | CTA FE | 14345000 | 15779500 | 23SLJ01-04 | 2024-09-11 | 2024 | 9 | 2024-09-26 | 15779500 | Y | CO24-179
AIMS-SA-033.v4_20240909 | 업무 완료 | 14345000 | 15779500 | 23SLJ01-04 | 2025-11-07 | 2025 | 12 | 2025-12-18 | 15779500 | Y | CO125-021
AIMS-SA-033.v4_20241021 | CTA FE | 6090000
AIMS-SA-033.v4_20241021 | 업무 완료 | 6090000
AIMS-SA-033.v4_20241103 | CTA FE | 8250000 | 9075000 | 23SLJ01-06 | 2024-11-06 | 2024 | 11 | 2024-11-28 | 9075000 | Y | CO24-253
AIMS-SA-033.v4_20241103 | 업무 완료 | 8250000 | 9075000 | 23SLJ01-06 | 2025-11-07 | 2025 | 12 | 2025-12-18 | 9075000 | Y | CO125-022
AIMS-SA-033.v4_20250828 | CTA FE | 14460000
AIMS-SA-033.v4_20250828 | NCA 기반 작업 제출 및 승인 | 21690000
AIMS-SA-033.v4_20250828 | 중간 분석 완료 (4unit, 10cohorts 기준) | 21690000
AIMS-SA-033.v4_20250828 | 최종 분석 완료 (2unit, 4 cohorts 기준) | 14460000
AIMS-SA-033.v4_20251107 | CTA FE | 17466000 | 19212600 | SLJ01-25-03 | 2025-11-20 | 2025 | 11 | 2025-11-27 | 19212600 | Y | CO125-007
AIMS-SA-033.v4_20251107 | 중간 분석 (5 cohorts) | 29561000 |  | SLJ01-25-03
AIMS-SA-033.v4_20251107 | 분석 reconcile, 업무완료 | 25273000 |  | SLJ01-25-03
AIMS-SA-033.v4_20260126 | 계약변경합의서 승인 | 8160000 | 8976000 | SLJ01-25-03-C02 | 2026-01-29 | 2026 | 2 | 2026-02-05 | 8976000 | Y | CO126-011
| Total | 367130000

## 11. Cytel (hidden)
11. Cytel
| Contract Number: |  | Version & date:
Protocol No: TTK-CS-101 |  |  | Updated on:
1. Total Payment Status
Category | $ | %
Budget | 0
Paid | 0 | #DIV/0!
Remaining | 0 | #DIV/0!
2. Yearly and Monthly Payment
| USD | KRW
2025 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 0
01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Costs Details
Contract # | Milestones | Budget Amount($) | Invoiced Amount($) | Invoice # | Invoiced Date | Paid Year | Paid Month | Paid Date | Total Amount(($) | Paid (Y) | 지출결의 #
| Total | 0